## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
20/01 | 2020-07-15 | 20/065 | Follow-up with NHSX the bid for funding to develop methods for the evaluation of technologies with embedded AI. | GL | TBC | This has been followed up but the timing for a further bid has been put back to later in the year. Funding has also been sought through the CSR process. | Closed | 2021-01-27
20/02 | 2020-07-15 | 20/070 | The scope for NICE to tackle health inequalities to be explored further as part of the current work to develop a 5 year strategy, and consideration given to seeking an external view on whether NICE could do more in this area. | GL/PC | 2020-12-01 | Tackling inequalities has been added as a core element to the 5 year strategy. | Closed | 2021-01-27
20/03 | 2020-07-15 | 20/072 | Audit & Risk Committee's terms of reference to be amended to include provision for an external member. Terms and conditions for the external member to be finalised, if the position is required following the outcome of the NED appointments. | SN | 2021-04-01 | Amendments to the terms of reference drafted. Issue now on hold pending outcome of NED recruitment. | Open | n/a
20/04 | 2020-09-16 | 20/085 | Review the equalities implications of virtual recruitment interviews. | JH | 2021-01-01 | We will be reviewing the evidence of the EDI implications of virtual recruitment as part of the equalities agenda. Plans to address this will be set out in the action plan once more evidence and options have been considered. | Open | n/a
20/05 | 2020-09-16 | 20/087 | Revised digital workplace business case to be brought to the Board following the work to: • clarify the sequencing of the transformation activities and how this can de-risk the investment • scrutinise the costs and review the use of external expertise to ensure this offers value for money, taking account of external benchmarking • clarify the centrality of the programme to the NICE Connect vision • further articulate the scale of the business process transformation and cultural change it will introduce for NICE. | AT | 2021-04-01 | The due diligence of the business case presented in September was completed. This led to a recommendation to initiate some of the work from the original 'foundational phase' in early 2021 in order to bring an updated business case back to the Board in April 2021. | Open | n/a
20/06 | 2020-09-16 | 20/088 | NICE's response to the IMMDS review to be publicised on the website. | JG | 2020-11-01 | NICE's response and a blog from Kevin Harris has been published on the website. | Closed | 2021-01-27
20/07 | 2020-11-18 | 20/097 | Lessons learnt from NICE's response to the pandemic to be shared with the Board. | GL | 2021-01-01 | Information to be included in Chief Executive's update to the Board at the morning session. | Closed | 2021-01-27
20/08 | 2020-11-18 | 20/102 | Next Health and Social Care Directorate progress report to include further information on the level of ambition for engagement activity, such as the social care podcasts. | JR | 2021-03-01 | The ambition for engagement will be now be reported in March to ensure alignment with the strategy. | Open | n/a
20/09 | 2020-11-18 | 20/102 | Progress update on NICE’s work on the national library of quality indicators to be circulated to the Board outside of the meeting. | JR | 2020-11-01 | An update was sent to the Chairman and the requesting board member. | Closed | 2021-01-27
20/10 | 2020-11-18 | 20/103 | Future updates on the Connect programme to provide a more externally focused overview of progress. | JH | 2021-01-01 | Actioned for next Board report, submitted to January Board meeting. | Closed | 2021-01-27
20/11 | 2020-11-18 | 20/104 | Directors' reports to include an update on the key risks to delivery in their respective centre/directorate. | SMT | 2021-01-01 | Added to the directors' reports for January. | Closed | 2021-01-27
20/12 | 2020-11-18 | 20/108 | Board to receive further information in January on the review of the recruitment process with a focus on increasing the diversity of appointees. | JH | 2021-01-01 | We have put together a draft EDI action plan with the initial priority on recruitment. The plan will be shared with the Executive Team in January. | Open | n/a
20/13 | 2020-11-18 | 20/109 | Board's implementation 'deep dive' in December to consider the scope to look at whether there are consistent themes across the impact reports. | JR | 2021-05-01 | Consideration of whether there are consistent themes across impact reports is in progress and the findings will be reported in a future H&SC Board report. | Open | n/a

## Closed
Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
2020-05-20 | 20/045 | Further reference to social care to be added to the business plan prior to submission to the SDS at DHSC for sign-off. | GL | 2020-06-01 | Business plan updated and approved by SDS on 3/6/2020. Now available on NICE website. | Closed | 2020-07-15
2020-05-20 | 20/049 | Risk management policy to be amended to include reference to learning from unforseen events. | CW | 2020-05-01 | Policy updated and issued on 22/5/2020. | Closed | 2020-07-15
2020-07-15 | 20/061 | Board to receive an update on the plans for restarting the use of the offices. | CW (JH) | 2020-08-01 | Update provided to the August Board Strategy meeting. The Manchester office will re-open on the 8 October for a phased return. | Closed | 2020-09-16
2020-07-15 | 20/066 | Board to receive further update on NICE’s work to support social care with the COVID-19 pandemic. | JR | 2020-09-01 | Information provided in the Health and Social Care Director's report. | Closed | 2020-09-16
2020-07-15 | 20/066 | Board to receive further update on the progress of discussions with the Care Quality Commission (CQC) about referencing NICE guidance in the CQC’s emergency support framework. | JR | 2020-09-01 | Information provided in the Health and Social Care Director's report. | Closed | 2020-09-16
2020-07-15 | 20/067 | Data on selected workforce indicators such as sickness and employee relations broken down by gender and ethnicity, to be provided to the Board. | CW (JH) | 2020-09-01 | Data is provided in the resources report. | Closed | 2020-09-16
2020-07-15 | 20/060 | Board to receive further update on the outcome of the pilot evaluation of digital health technologies. | MB/HK | 2020-11-01 | Scheduled for the November Board meeting. | Closed | 2020-11-18
2020-09-16 | 20/083 | Statement on the impact on NICE of the end of the transition agreement to be shared with the Board prior to publication on the NICE website. | JG | 2020-11-01 | This has been circulated to Board members. | Closed | 2020-11-18
2020-09-16 | 20/084 | Board to receive an update on the engagement with the Association of Directors of Adult Social Services in England and Skills for Care. | JR | 2020-11-01 | Engagement is ongoing with a number of colabarative projects. For example we are working with Skills for Care, the Local Government Association and the Association of Directors of Adult Social Services on a new national working group to promote and support wellbeing across the social care workforce. | Closed | 2020-11-18
2020-09-16 | 20/088 | IMMDS review's findings to be used as an opportunity to work with partners to reinforce the importance of NICE’s interventional procedures guidance. | JR/KH | 2020-11-01 | An update on NICE's patient safety activity is presented at the November Board meeting. | Closed | 2020-11-18