## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
21/38 | 2021-11-17 | 5 | Board to receive further information on the scope to utilise the prototype equity impact calculator developed with the University of York and the outcome of the current review of NICE’s approach to addressing health inequalities. | JR | 2022-03-01 | Information provided to the March Board seminar. | Closed | 2022-03-17
21/41 | 2021-11-17 | 9 | Further information to be provided to the Board on how the transferring staff from the NGA and NGC will support delivery of the new guidelines operating model, and the impact on the relationships with the two Royal Colleges. | PC | 2022-06-01 | The TUPE process is being managed by a programme board. New operating models are being explored for the transition to topic suites, supported by centralised centres of excellence. | Open | n/a
22/01 | 2022-01-19 | 6 | Look at what further action could be taken to avoid an underspend similar to 2021/22 in 2022/23. | JH | 2022-03-01 | NICE has continued to explore all opportunities to make effective use of the funding available to it in the current year. The current year underspend is now forecast to be less than £1m which is already a substantial improvement on the prior year and given an overspend is not permitted there will always be some level of underspend. The financial position moving into next year remains uncertain but is expected to be significantly more constrained. Nevertheless, we continue to review and prioritise our investment opportunities so that as soon as funding is available we have plans in place to utilise effectively. | Closed | 2022-03-17