## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
21/41 | 2021-11-17 | 9 | Further information to be provided to the Board on how the transferring staff from the NGA and NGC will support delivery of the new guidelines operating model, and the impact on the relationships with the two Royal Colleges. | PC | 2022-09-01 | Sustainable future operating models to accommodate new ways of working for guideline production are being explored as a workstream for the objective to deliver digital living guideline recommendations. Progress update on the digital living guidelines priority presented to Board in June 2022, with further update in September. | Open | n/a
22/03 | 2022-03-17 | 7 | Board to receive an update on the outcome of the consultation on the real world evidence framework and the next steps. | FG | 2022-07-01 | Update following the consultation provided in the executive team report to the July Board. | Closed | 2022-07-22
22/04 | 2022-03-17 | 8 | Board to be updated when the health inequalities oversight group has confirmed any changes to NICE’s approach in light of the NICE Listens recommendations. | JR | 2022-10-01 | NICE Listens recommendations complemented those from the external consultant who carried out an engagement exercise with strategic partners therefore recommendations have been incorporated into the health inequalities priorities for 2022/23. A progress update against the priorities will be reported to the Board at the end of Q2. | Open | n/a
22/05 | 2022-05-25 | 5 | Session to be held with the NEDs to discuss learning from the AMR project, including what worked well and what didn’t. | FG | 2022-07-01 | Briefing provided to the July Board seminar. | Closed | 2022-07-22
22/06 | 2022-05-25 | 5 | Board to receive an update on hybrid working when qualitative and quantitative data is available on whether the working arrangements both provide flexibility for staff and support the delivery of the transformation programme. | NG | TBC | Update to be provided when further information is available. | Open | n/a
22/07 | 2022-05-25 | 5 | Board to receive an update on the general themes in the feedback from the consultation on the real world evidence framework and how the framework will now be applied, including as part of the business plan priority to develop and launch a new early value assessment approach for medical devices, diagnostics and digital products. | FG | 2022-07-01 | Update provided in the executive team report to the July Board. | Closed | 2022-07-22
22/08 | 2022-05-25 | 6 | Board to receive a bridge analysis explaining the variance between planned and outturn income in the TA/HST programme. | JH | 2022-07-01 | Analysis provided as an appendix to the integrated performance report. | Closed | 2022-07-22
22/09 | 2022-05-25 | 6 | Board to receive further information on whether the increased number of terminated guidance in 2021/22 is likely to be repeated in future years. | HK | TBC | Verbal update to be provided to the Board. | Open | n/a
22/10 | 2022-05-25 | 6 | Board to receive an update on the long-term funding mechanism for ILAP at a suitable point in the future. | HK | TBC | Verbal update to be provided to the Board. | Open | n/a
22/11 | 2022-05-25 | 6 | Board to receive information on whether turnover is affecting particular roles or parts of the organisation and also whether exit interviews have raised any common themes. | NG | 2022-07-01 | Information added as an appendix to the integrated performance report. | Closed | 2022-07-22
22/12 | 2022-05-25 | 7 | Board to discuss the lessons learnt from the work on dynamic living guidelines at a future seminar. | PC | 2022-09-01 | To be covered as part of the update on the business plan priorities at the September Board seminar. | Open | n/a
22/13 | 2022-05-25 | 7 | Further information to come back to the Board on the proposed approach for producing TA guidance more quickly as part of the business plan priority on proportionate approach. | HK | 2022-07-01 | Covered as part of the deep-dive at the July Board seminar. | Closed | 2022-07-22
22/14 | 2022-05-25 | 7 | Board to receive further information on the learning objectives for the work under business plan priority 3 on early value assessment. | JK | 2022-06-01 | Covered as part of the deep-dive at the June Board strategy meeting. | Closed | 2022-07-22
22/15 | 2022-05-25 | 8 | Board to receive information on the results of phishing simulations undertaken at NICE. | AT | 2022-09-01 | An update on phishing simulation will be provided at the next Audit and Risk Committee in September. | Open | n/a