## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
20/03 | 2020-07-15 | 20/072 | Audit & Risk Committee's terms of reference to be amended to include provision for an external member. Terms and conditions for the external member to be finalised, if the position is required following the outcome of the NED appointments. | SN | 2021-04-01 | External member appointed to the Audit & Risk Committee with effect from 1 April 2021. | Closed | 2021-03-24
20/04 | 2020-09-16 | 20/085 | Review the equalities implications of virtual recruitment interviews. | JH | 2021-04-01 | We will be reviewing the evidence of the EDI implications of virtual recruitment as part of the equalities agenda. Plans to address this will be set out in the action plan once more evidence and options have been considered. | Open | n/a
20/05 | 2020-09-16 | 20/087 | Revised digital workplace business case to be brought to the Board following the work to: • clarify the sequencing of the transformation activities and how this can de-risk the investment • scrutinise the costs and review the use of external expertise to ensure this offers value for money, taking account of external benchmarking • clarify the centrality of the programme to the NICE Connect vision • further articulate the scale of the business process transformation and cultural change it will introduce for NICE. | AT | 2021-04-01 | The due diligence of the business case presented in September was completed. This led to a recommendation to initiate some of the work from the original 'foundational phase' in early 2021 in order to bring an updated business case back to the Board in April 2021. | Open | n/a
20/08 | 2020-11-18 | 20/102 | Next Health and Social Care Directorate progress report to include further information on the level of ambition for engagement activity, such as the social care podcasts. | JR | 2021-03-01 | Ambition for engagement activity will be included in Board reports going forward to ensure context. | Closed | 2021-03-24
20/12 | 2020-11-18 | 20/108 | Board to receive further information in January on the review of the recruitment process with a focus on increasing the diversity of appointees. | JH | 2021-04-01 | We have put together a draft EDI action plan with the initial priority on recruitment. The plan will be shared with the Executive Team in February. | Open | n/a
20/13 | 2020-11-18 | 20/109 | Board's implementation 'deep dive' in December to consider the scope to look at whether there are consistent themes across the impact reports. | JR | 2021-05-01 | Consideration of whether there are consistent themes across impact reports is in progress and the findings will be reported in a future H&SC Board report. | Open | n/a
21/1 | 2021-01-27 | 21/007 | Board to receive further information on the actions to address the vacancies. | JH | 2021-03-01 | Summary on workforce planning included in March Resources report. Proposals due to go to ET in April. | Open | n/a
21/2 | 2021-01-27 | 21/009 | Board to receive further information on the measures that will be used to quantify the success of the Innovative Licensing and Access Pathway. | FG | 2021-03-01 | Measures of success for ILAP currently being developed by MHRA, NICE and SMC, and will be reviewed at next joint ILAP steering group. We suggest that these might be a good topic for review at the joint MHRA/NICE board meeting in October. | Open | n/a
21/3 | 2021-01-27 | 21/011 | Board to consider at February Board Strategy meeting whether the new values and behaviours sufficiently align with the new strategy. | GL | 2021-02-01 | Discussed as part of the Chief Executive's update in February. | Closed | 2021-03-24
21/4 | 2021-01-27 | 21/013 | Meindert Boysen, Gill Leng and Sharmila Nebhrajani to discuss the timing for the process review consultation outside of the meeting to take account of the pressures within NICE and the wider health and care system, and to ensure alignment with the methods review | MB/GL/SN | 2021-01-01 | Consultation started on 4 February, but due to the Government restrictions, the consultation period was extended to allow stakeholders more time to consider their responses, and closes on 15 April. | Closed | 2021-03-24
21/5 | 2021-01-27 | 21/014 | Board to receive regular progress updates on the Data and Analytics, Methods and Standards Programme and Implementation plan | FG | 2021-05-01 | Progress updates will be provided in the SEA directorate progress reports. | Closed | 2021-03-24
21/6 | 2021-01-27 | 21/017 | Board to receive an update on the arrangements for managing the risk around cyber security, in the context of the merger of the IT and Digital Services teams under the Digital, Information and Technology Directorate, and the environment of rapid change. | AT | 2021-02-01 | Latest annual report to the Audit & Risk Committee sent to the Board for information. Further update to be provided to the Board in May. | Closed | 2021-03-24