## Slide 1: Integrated performance report
March 2024

## Slide 2: Contents
Section | Slide / chart number | ET lead
Our transformation objectives in the 23/24 business plan NICE-wide horizon scanning and topic selection Early engagement with industry Improving our digital presence Incorporating technologies into guidelines and resource impact Advice on HealthTech products Improvements to methods and processes Improving measurement Continuous improvement and talent management | Slide 5 Slide 5 Slides 6 & 7 Slides 6 & 7 Slides 6 & 7 Slide 8 Slide 9 Slide 10 | Jonathan Benger Mark Chapman Paul Chrisp Jonathan Benger Mark Chapman Helen Knight Clare Morgan Sam Roberts
Producing high quality advice… | Slide 12, chart 1 Slide 12, chart 2 Slide 13, charts 3 & 4 | Helen Knight Mark Chapman Jonathan Benger
…that is relevant | Slide 14, chart 5 Slide 14, chart 6 | Mark Chapman Clare Morgan
… that is timely | Slides 15, 16, 17 & 18 Slide 19, charts 10 & 11 Slide 19, chart 12 | Helen Knight Mark Chapman Nick Crabb
… that is useable and has a demonstrable impact | Slide 20, chart 13 Slide 20, chart 14 Slide 20, chart 15 | Boryana Stambolova Raghu Vydyanath Clare Morgan
While ensuring happy and well supported staff… | Slides 22, 23 & 24 | Helen Brown
…effective communications and engagement | Slide 25, chart 23 Slide 25, chart 24 Slide 26, chart 25 Slide 26, charts 26 & 27 Slide 27, chart 28 & 29 | Clare Morgan Jane Gizbert Boryana Stambolova Jane Gizbert Jane Gizbert
… and a financially sustainable organisation | Slides 28, 29, 30 & 31 | Boryana Stambolova

## Slide 3: Summary
Area
Confidence in achieving targets at year end
Comments
Our transformation objectives in the 23/24 business plan
At the end of February, 3 business plan objectives have been achieved (developing a new approach to prioritising guidance; simplifying how we engage and support industry; and adopting a NICE-wide approach to talent management). The remaining objectives are rated amber while issues that emerged are resolved, although we are still on course for the most part to achieve their intent. The objective about continuous improvement was retired in 2023 due to financial pressures. Of the 50 milestones in the business plan, 27 have been achieved and a further 13 are on track for delivery next month. Six are at risk, and just 4 milestones will not be delivered.
High quality advice that is relevant, timely, usable and has a demonstrable impact
It is anticipated that the guidelines and health technologies programmes will deliver the volume of outputs in the 2023/24 business plan, with the number of guidelines outputs significantly ahead of target. The number of quality standards updates will be lower than set out in the business plan but in line with internal work-plans. It is anticipated that the final number of technology appraisal (TA) and highly specialised technologies (HST) outputs will be 90% of the business plan target.
YTD, the mean and median number of days between GB marketing authorisation (MA) and TA/HST guidance publication has significantly reduced from 2022/23 for ‘optimal’ topics and the 15% target reduction is likely to be met. However, this target is unlikely to be achieved when ‘divergent’ topics are included, with performance affected by 6 HST publications with a mean of 1,625 days. The target to produce conditional recommendations for early value assessments within 6 months is also unlikely to be met. The proportion of early engagement services that are for diagnostics, devices and digital technologies has slightly increased from 2022/23, but the target for a 25% increase is at risk of delivery.
While ensuring a financially sustainable organisation, with happy and well-supported staff, and effective communications and engagement
At the end of month 10 the year to date overspend is £0.98m, primarily driven by under recovery against plan for TA income (£2.2m). The forecast outturn is currently a £0.56m surplus, with a worst-case scenario of a £0.14m underspend and a best-case scenario of £0.97m underspend.
Sickness absence has increased over the winter months and the YTD figure is now above target and 2022/23 levels. Staff turnover remains slightly above target but lower than last year. There are no significant concerns with the year-end forecast for the other people indicators or the communications and engagement indicators, although the outturn performance may be slightly below plan for several indicators.

## Slide 4: Our transformation objectives in the 2023/24 business plan
1 April 2023 to 29 February 2024

## Slide 5: Transformation Progress – February 2024 (Slide 1 of 5)
Focus on what matters most
1
Relevance
Objective 1
Increase the relevance of our guidance by developing a NICE-wide horizon scanning & topic selection function enabled by coordinated stakeholder engagement
Objective 2
Increase the real-world impact of our pre-evaluation support by simplifying and improving NICE’s early engagement with industry
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Delivered an external webinar on 12 Feb - attended by nearly 1000 stakeholders.
Completed 3 rounds of testing the framework.
Draft consultation paper reviewed by ET, Board and Prioritisation Board and at the Board seminar, and shared with Dept of Health & Social Care and NHSE sponsor teams.
Approach to enhanced horizon scanning for meds in response to international recognition procedure (IRP) confirmed in consultation with Association of British Pharmaceutical Industry.
New pipeline tracker service procured and tested, with initial US Food & Drug Administration (FDA) pipeline/ Pharmascan cross ref reports in development for use in pipeline meetings in April.
A high-level insight report based on intelligence gathered in Q3 has been produced.
System intelligence has been gathered and incorporated into the position statement on social care.
Objective 2:
Continued increases seen in enquiry numbers for NICE Advice.
All-team strategy day held to unite the team and build morale. Engagement with Health Innovation Network, with plan to work together to support the 8 Innovative Devices Access Pathway pilot technologies and deliver a series of knowledge exchange. workshops.
Income targets set for 24-25.
Key risks and challenges
Objective 1:
Successful establishment of a fully functional 'topic intelligence and monitoring team' in the clinical directorate and the integration of Topic Selection Oversight Panel into the Prioritisation Board.
External challenge to the proposed clarification process during or after the formal consultation.
Objective 2:
Continued delay in getting Senior Account Manager in post.
High uncertainty and flux in staff positions due to range of factors including maternity leave, sickness, career breaks and secondments, which is creating challenges for workforce and financial planning, as well as causing disruption for the team.
What we have learnt
Objective 1:
The layers of complexity that surround the suggestion to move from a challenge process to a common clarification process when the prioritisation board is established.
Objective 2: Although secondments and career breaks support people’s development, they can put considerable pressure on the team.
8 | Milestone | Delivered by | On track?
 | Adopted a new, coordinated approach to stakeholder engagement ​​ | Feb 2024 | Yes​
 | Redesigned our support for developers and innovators to make the most of NICE’s relevant services, better tailored to the needs of all types of technology developers​​ | Oct 2023​ | Yes​
 | Established a new early engagement team bringing together all of NICE’s industry engagement services ​ | Nov 2023 | Yes – Prog Board agreed revised date of Nov 23
 | Redesigned our business model to allow more scope for proactive outreach and to facilitate risk-based proportionate approaches to our advice for technologies ​ | Nov 2023​ | Yes​
 | Established new ways of working to systematically gather intelligence from the health and social care system, and from life sciences and industry ​​ | Feb 2024​ | Yes​
 | Created a cross-organisational prioritisation function ​​ | Jan 2024​ | Yes​
 | Established a new mechanism to scope and schedule our topics based on identified priorities ​​ | Jan 2024​ | Yes​
 | Tested our selected priorities with the health and care system ​ | Feb 2024​ | Yes​

## Slide 6: Transformation Progress – February 2024 (Slide 2 of 5)
Provide useful and useable advice – Part 1
Useable
Objective 3
Make our advice easier to access by improving our digital presence
Objective 4
Increase the useability of our guidance by incorporating technologies into guidelines, and evolve our supporting resource impact assessment
Objective 5
Improve the value of NHS purchasing in new ways by developing the programme to provide advice on classes of HealthTech products already in use
2
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Objective 3:​
Product and channel strategy (how we deliver NICE’s content to our users): Vendor meetings have been held in relation to our Prior Information notice (PIN) – this signals our intention to undergo procurement for a knowledge platform to deliver NICE’s content. Workstreams and objectives are being scoped as part of our 24/25 business planning. ​
The project to establish a Componentised Content Management System (CCMS) – which would enables a more flexible and efficient approach to updating our content has progressed with completion of a business case and tender specification.
Corporate website and Content Management System (CMS): ​
Continues to make good progress with the corporate website and remains on track to launch the new homepage in early April. ​
​Internal communications commenced to highlight the content freeze and the launch of the homepage . A "learn a bit about" session on the new homepage was held on 29 February.​ Further work on migration, template design, and setting website metrics carried out.​​
Objective 4: ​
External webinar held with 150+ stakeholders to explain the approaches to including Technology Appraisals (TAs) into guidelines​.
External stakeholder consultation started on interim methods and process statement (running from 5 February to 5 April 2024).​
A new webpage produced setting out our approach to bringing guidance together​.
Work is ongoing to develop processes and resourcing for complex incorporation.​
Additional integration pilot topic confirmed (Chronic heart failure)​.
New resource impact assessment (RIA) template developed and now in use after consultation with multiple stakeholders​.
Objective 5:​
The approach has been approved by Guidance Executive (GE). Interim Methods & Processes now open for 4 weeks consultation. Interim process and methods have been shared with NICE’s legal advisers, who recommend this now proceeds into consultation.
Tier 2 pilots are now almost agreed – wound-care topics to be finalised.​
Key stakeholders for the topic have been identified for NHS Supply Chain (NHSSC) /National Institute for Cardiovascular Outcomes Research (NICOR) and NHSE​. Working relationship established with NHSSC, in progress for NICOR and NHSE​.
Chair of Interventional Procedures Advisory Committee (IPAC) recruited to Chair the topic (scoping workshop and committee meetings)​.
DHSC/NICE Memorandum of Understanding (MOU) signed 20 February 2024 - payment to be processed (March 2024)​
Key risks and challenges
Objective 3: ​
CCMS: Risk that the market response to the PIN is not of sufficient quality and breadth to ensure competition and enable us to achieve our objectives around content management.
The migration to a new service and supporting business processes​ needs to be well planned and communicated.
Corporate website: Risk currently being monitored on web team resource capacity. ​
Objective 4: ​
Risk to continuity and resourcing because of the Centre for Guidelines management of change process​.
Risk of delay to agreeing an approach to commercial engagement with NHSE​.
Risk of pilot timeline slipping if volume of commercial engagement is high. ​
Risk of legal challenge on the proposed approach to integration​.
Risk of pilot timelines slipping due to complexity and volume of reviewing work required.​
Risk of pilot timelines extending because of challenge of obtaining papers from British Library​. Overall delay to timelines for publishing the finalised methods and process statement due to extended timelines for the pilot topics.​​
Objective 5​
Late-Stage Assessment (LSA) is a new NICE approach, which means there is a degree of estimation in the costings to deliver the pilots, and there is a risk these costs could increase during the production of the NICE guidance.​
There are resource and capacity constraints on project support. Increased engagement, level of feedback and interest from stakeholders around our methods and processes means the consultation is to run longer than originally expected (Feb/March 24) to allow greater opportunity for feedback to be obtained.​
Delays in data access. Infrastructure to deliver timely access doesn't meet the ambition.
What we have learnt
Objective 3:​
Corporate website: It is important that the new homepage meets user and business needs, promotes NICE's brand and reputation, and communicates NICE's vision and strategic objectives.
​It is important to maintain involvement and effectively communicate progress on the knowledge platform​ given the importance and impact of this work.
Objective 4: ​
An additional pilot/s may be required to ensure that the approach to integration can be robustly tested (eg quantitative modifiers). ​
End users are finding it challenging to be ready by the end of the 90 day implementation period – this is due to a range of factors including changes to the pathway, capacity constraints, the volume of TAs, and funding.
Objective 5​
We need to allow more time for stakeholders to provide us with feedback. Responses indicated that two weeks was not enough time to provide detailed feedback from our stakeholders and therefore we have increased our timeline for this consultation to four weeks.

## Slide 7: Transformation Progress – February 2024 (Slides 3 of 5)
Provide useful and useable advice - Part 2
2
17 | Milestone | Delivered by | On track?
 | Objective 3: Make our advice easier to access by improving our digital presence |  | 
 | Commenced rolling quarterly improvements to guideline content presentation based on user research ​​ | Jul 2023 | Yes
 | Procured a new Content Management System (CMS) to enable improvements to NICE’s corporate website | Aug 2023 | Yes
 | Created a product and channel strategy to describe the future publishing model for NICE guidance that is more useful and useable | Oct 2023 | Yes
 | Commenced the continuous deployment and integration phase of our new CMS adoption | Oct 2023 | Yes
 | Procured suitable content management technology to realise our product strategy and deliver more value to our guidance users | Nov 2023 | No
 | Objective 4: Increase the useability of our guidance by incorporating technologies into guidelines, and evolve our supporting resource impact assessment |  | 
 | Agreed an approach to capturing and reporting evidence about the capacity and workforce implications of an intervention or recommendation | Jun 2023 | Yes
 | Aligned relevant methods and processes between guidelines and Technology Appraisals | Sept 2023 | Yes
 | Agreed and published interim methods and processes | Nov 2023 | No
 | Commenced 2 pilots of interim principles for integrating Technology Appraisals (TAs) in guidelines | Feb 2024 | No
 | Developed and tested a new presentation approach to illustrate the workforce and capacity implications of NICE advice | Nov 2023 | Yes
 | Developed and adopted a Resource Impact Analysis methodology that reflects more granular evidence about capacity and workforce implications | Nov 2023 | Yes
 | Finalised and published the updated methods manual codifying the new approach | Mar 2024 | No
 | Objective 5: Improve the value of NHS purchasing in new ways by developing the programme to provide advice on classes of HealthTech products already in use |  | 
 | Publication of the LSA interim processes and methods statement and the comms plan | Feb 2024 | Yes
 | Developed new methods and processes to consider late-stage multi-tech evaluations | Dec 2023 | Yes
 | Developed an approach to accessing and utilising data for late-stage class-based evaluations | Dec 2023 | Yes
 | Launched two pilots of the new approach and planned launches for remaining topics | Mar 2024 | Yes
 | Developed partnerships for longer-term delivery of data access | Mar 2024 | Yes

## Slide 8: Transformation Progress – February 2024 (Slide 4 of 6)
Provide useful and useable advice - Part 3
Timely
Objective 6
Improve the timeliness of our guidance by implementing improvements to our methods and processes identified last year
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Work to identify and actively monitor the Key Priority Areas (KPAs) within agreed topic suites continues, to ensure we focus on what matters most. Diabetes, Women's health are functioning as envisaged in the digital living guidelines (DLG) model. ​
​
Useful and Useable Programme Board presentation on cross NICE consultation work. Request to consider further as part of business planning and 24/25 objective to align relevant processes. ​
​
Agreement reached on plan to establish mental health suite. Other 3 high priority suites already established. ​
​
The first modular update to the Guide to developing Health Technology Evaluation was published on 31 October 2023.
The 15% target reduction of the mean and median number of days between GB marketing authorisation (MA) and TA/HST guidance publication is on track to be achieved for ‘optimal’ topics
Key risks and challenges
Work has begun on a new operating model for the Centre for Guidelines and there is a risk that this will slow progress and impact on delivery. ​
​
The impact of accelerated regulatory processes by the MHRA might impact on the overall timeliness KPI.
A number of divergent topics are taking have taken longer than the target time to reach publication.
There have also been challenges to produce conditional recommendations for early value assessment within their 6 months target.
What we have learnt
Work has begun on designing a new operating model for the Centre for Guidelines and there is a risk that this will slow progress and impact on delivery. ​
​
The impact of accelerated regulatory processes by the MHRA might impact on the overall timeliness KPI.
10 | Milestone | Delivered by | On track?
 | Health tech: Launched the first topic under a new single approach to multi-technology evaluations across medtech, diagnostics, and digital, including incorporating quick wins identified in our Early Value Assessment pilots | Aug 2023 | No
 | Guidelines: Embedded pilot living mechanisms to monitor evidence & system intelligence for Key Priority Areas within diabetes & women’s health suites | Aug 2023 | Yes
 | Health tech: Defined the approach to including Resource Impact Statements alongside all health tech guidance | Oct 2023 | Yes
 | Medicines: Published a modular update to our methods and processes to embed improvements identified in our Proportionate Approach to Technology Appraisals in 2022/23 | Oct 2023 | Yes
 | Guidelines: Tested new proportionate approaches to guideline updates following identification of new evidence in Key Priority Areas in diabetes suite | Dec 2023 | Yes
 | Guidelines: Implemented a proportionate approach to consultation across all priority guideline suites | Jan 2024 | Partially
 | Medicines: Confirmed an approach to enable Rapid Entry to Managed Access | Jan 2024 | No
 | Medicines: Developed two reference models to test pathway appraisals in cancer medicines | Jan 2024 | Yes
 | Medicines: Commenced a pilot of a new approach to immuno-oncology appraisals/portfolio appraisals | Mar 2024 | No
 | Guidelines: Created a faculty of experts to support lifecycle of recommendations in 5 priority topic suites | Mar 2024 | Partially
2

## Slide 9: Transformation Progress – February 2024 (Slide 5 of 6)
Constantly learning from data and implementation
3
Learning from real
world data
Objective 7
Support implementation of our guidance by improving our measurement approach, and develop an automated uptake and monitoring system in a priority topic
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Implementing routine measurement​
The uptake data directory format has been agreed and templates set. This includes national uptake figure, the frequency the data is updated, and the opportunity the data gives for more detailed insights​.
​
Automation/Computability ​
Focus has been on business planning and particularly how computability and automated reporting is built into Science, Evidence, & Analytics (SEA) business objectives for 2024/25​.
Explored initial conversations with the content team to ensure that priorities align on computability for 2024/25.​
Explored options to use large language models to build parts of Digital Adaptation Kits (i.e. computable recommendations).
.
Key risks and challenges
Business planning for different components of products and channels (where computability will “sit”) have been developed separately. It is important that these align as we finalise business plans.
What we have learnt
Our internal audiences want direct access to high level information and insights from measurement.
6 | Milestone | Delivered by | On track?
 | Assessed the extent of uptake of priority guidance using currently available data | Sep 2023 | Yes
 | Develop an automated data pipeline to illustrate variation in clinical practice in primary care | Dec 2023 | Yes
 | Develop an approach for automatic measurement of core recommendations in NICE guidance (Health Technology Assessment (HTA) + guidelines) | Dec 2023 | Yes
 | Developed an approach for defining core computable recommendations for guidance | Mar 2024 | Yes
 | Implemented routine measurement of TAs and high impact/priority TAs quality standards as a surrogate for guideline uptake ​ | Mar 2024 | Yes
 | Established a system for routine feedback from uptake data to inform implementation support plans and topic selection | Mar 2024 | Yes

## Slide 10: Transformation Progress – February 2024 (Slide 6 of 6)
Build a brilliant organisation
4
Brilliant organisation
Objective 8
Build a brilliant organisation by implementing suggestions from crowdsourcing and staff survey including: develop a continuous improvement process and capabilities and adopt NICE-wide talent management approach
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Wellbeing Conversations Training for managers continues. As of 16 Feb, manager confidence level is 8.1/10.​
A new Management Development Programme cohort started in January, with Module 2 delivered on 07/02.​
The Exec Team attended a further in-person module on 08/02 as part of their Leadership Development Programme.​
The People Team attended Diversity and Wellbeing Training with the Knowledge Academy 6-8 Feb, plus directorate development days 12-13 Feb.​
Corporate Induction was delivered to 8 new starters on 14/02. The Recruitment Team also attended the session, with a view to refreshing and improving the induction process for 24/25.​
Learning and Organisational Development are facilitating the Change Network Development Session on 20/02.​
Succession Planning training took place for ET on 27/02.​
Work continues to support the DHSC/ALBs Talent Management Workstream. A networking event took place on 29/02.​
The Career Conversations evaluation has been completed.
Work is underway to host 2 x interns as part of the Health Data Science Black Internship Programme 2024. Shortlisting and interviewing taking place in February.
Key risks and challenges
A concern has been raised about colleagues inappropriately using the NICE values. A proposal to address this has been designed and will be presented to ET.
What we have learnt
6 | Milestone | Delivered by | On track?
 | Completed our automation/Artificial Intelligence (AI) strategy to improve our ways of working | Oct 2023 | Yes
 | Developing a 2-5 year Equality, Diversity and Inclusion roadmap | Nov 2023 | Yes
 | Redesigned our performance management process to streamline processes, embed management competencies and improve feedback | Dec 2023 | Yes
 | Launched a new intranet to support out transformation messaging and provide a networking and community building vehicle for staff | Dec 2023 | Yes
 | All directorates working with SharePoint instead of network drives on production of new information and docs | Dec 2023 | Yes
 | Developed a talent management approach including talent identification and succession planning | Jan 2024 | Yes

## Slide 11: Provide high quality advice, that is relevant, timely, usable, and has a demonstrable impact
1 April 2023 to 31 January 2024

## Slide 12: Provide high quality advice…
Chart: Chart 1: 110 technology appraisal and highly specialised technologies guidance
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 5 | 12 | 14 | 6 | 1 | 3 | 13 | 8 | 9 | 6 | 0 | 0
22/23 | 6 | 5 | 12 | 9 | 1 | 3 | 13 | 8 | 9 | 6 | 12 | 8
2023/24 plan | YTD actual | Year-end forecast RAG status
110 | 77 | A
Not expected to hit business plan target of 110 publications at this stage of the business year. It is expected the final number of publications will be 90% of the target.
Chart: Chart 2: 50 health technologies programme guidance
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 8 | 6 | 7 | 3 | 3 | 7 | 4 | 5 | 1 | 5 | 0 | 0
Plan | 8 | 6 | 7 | 4 | 3 | 6 | 4 | 5 | 4 | 2 | 6 | 1
22/23 | 2 | 4 | 3 | 3 | 6 | 3 | 3 | 7 | 1 | 6 | 3 | 5
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
49 | 49 | 100% | G
Expected to reach target.

## Slide 13: Provide high quality advice…
Chart: Chart 3: 17 new guidelines or updates to topic suites
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 1 | 3 | 3 | 2 | 3 | 5 | 9 | 3 | 1 | 3
Plan | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1
22/23 | 2 | 2 | 4 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
15 | 33 | 220% | G
Year-end target exceeded. Variance due to topics publishing earlier than planned and inclusion of 1 surveillance team generated update. In October, an additional 6 innovative updates have also been completed by the surveillance team which involved a change of content but did not require new evidence synthesis.
Chart: Chart 4: 11 quality standard updates
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 2 | 2
Plan | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0
22/23 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 2 | 3
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
6 | 7 | 117% | G
Variance due to additional topic being included in the work programme after annual planning had been agreed (Acute respiratory infection and virtual wards QS).

## Slide 14: …that is relevant
Chart: Chart 5: Increase the proportion of early engagement services provided for diagnostics, devices and digital technologies by 25%
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0.294 | 0.294 | 0.3333 | 0.31 | 0.27 | 0.3 | 0.3 | 0.3 | 0.3
Target for 23/24 out-turn | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36
22/23 out-turn | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
29% of engagements | 36% of engagements | 30% | A
Volume of requests from the pharma industry continue to affect progress with the KPI. Uptake of new 'surgery' service by healthtech industry has been slower than anticipated in the early stages but further sessions expected before the end of the FY which should improve the ratio.
Chart: Chart 6: Prioritised strategic stakeholders have a named relationship lead
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0.46 | 0.43 | 0.53 | 0.66 | 0.75 | 0.75 | 0.77
Target for 23/24 out-turn | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
0% | 80% | 77% | G
The KPI is based on prioritised strategic stakeholders who have been assigned a named relationship lead within NICE who has at a minimum undertaken a meeting or has a meeting scheduled within the business year. Performance has been affected by diary pressures for senior stakeholders.

## Slide 15: Helping practitioners and commissioners get effective treatments to patients fast
…that is timely
In 2022/23, NICE reduced the time taken to deliver guidance on medicines following GB marketing authorisation (MA) by 17%. In 2023/24, we aim to reduce the time by a further 15%.
Our ability to publish final technology appraisal or highly specialised technologies guidance within 90 days of a medicine gaining marketing authorisation depends on whether it is classified as ‘optimal’ or ‘divergent’.
Does the medicine meet all of the characteristics of an optimal topic?
Yes
Medicine is categorised as optimal
NICE can publish guidance within 90 days of GB MA
No
Medicine is categorised as divergent
NICE cannot publish guidance within 90 days of GB MA due to external factors

## Slide 16: How we characterise an ‘optimal’ or divergent topic
…that is timely
We categorise medicines as either optimal or divergent based on whether it is possible to publish final guidance within 90 days of marketing authorisation.
Characteristics of an ‘optimal’ topic
NICE is notified of topic >16 months ahead of GB marketing authorisation.
Company accepts the NICE topic selection or routing decisions.
Company does not negotiate a delayed evidence submission date.
The technical engagement stage is not required.
Additional data is not provided post evidence submission date.
Cost effective ICER presented and agreed at the first committee meeting leading to final draft guidance (consultation not required).
The topic is not delayed/paused due to commercial discussions (pre or post the committee meeting).
No appeal received for the topic or, if appeal received, appeal points are upheld.
There aren’t other external factors that cause delay to the appraisal timelines.

## Slide 17: Factors that cause topics to be ‘divergent’
Chart: %
| NICE notified of topic less then 24 months ahead of GB MA | Company negotiated delayed evidence submission date | Required further committee meetings after ACM1 | Company request (other) | Additional data provided post submission date | NICE capacity | COVID-19 pause | Appeal held | EAG capacity | Licencing | Topic delayed due to commercial discussions
2022-23 | 50 | 22 | 13 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0
2023-24 | 47 | 24 | 16 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2
Chart displaying the primary factors impacting NICE’s ability to publish timely guidance, displayed as a % of all factors

## Slide 18: Days between GB marketing authorisation and final TA/HST guidance publication: 1 April-31 January 2023
Chart: Mean
| Optimal: 2022-23 | Optimal: Target | Optimal: YTD | Divergent: 2022-23 | Divergent: Target | Divergent: YTD | All: 2022-23 | All: Target | All: YTD
2022-23 | 55 | 90 | 38 | 363 | 309 | 540 | 323 | 275 | 455
Chart: Median
| Optimal: 2022-23 | Optimal: Target | Optimal: YTD | Divergent: 2022-23 | Divergent: Target | Divergent: YTD | All: 2022-23 | All: Target | All: YTD
2022-23 | 62 | 90 | 46 | 322 | 274 | 371 | 284 | 241 | 322
Commentary
High confidence that the targets will be achieved for optimal medicine publications, as YTD performance is significantly lower than target. Already published more optimal topics YTD than the 22-23 year. Low confidence that mean and median targets for divergent and all topics categories can be achieved. TA publications (45) have a mean of 305 days, however HST publications (6) have a mean of 1,625 days which is significantly affecting the divergent and overall data for 23-24.
Figures in () indicate the number of topics in each category
Figures in () indicate the number of topics in each category
 | RAG
Optimal | Green
Divergent | Red
All | Red
(7)
(47)
(54)
(8)
(43)
(51)
(7)
(47)
(54)
(8)
(43)
(51)

## Slide 19: …that is timely
Chart: Chart 10: Time to produce health technology guidance is reduced by 17%
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 out-turn | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
22/23 out-turn | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
72 weeks | 60 weeks | 0 weeks | G
This target is expected to be reached with the development of a refreshed health tech guidance timeline. This timeline is currently in development and will be delivered by the end of the business year.
Chart: Chart 11: Conditional recommendations for early value assessments (EVAs) are produced within 6 months
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 out-turn | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
n/a | 80% | 0% | R
No EVAs have yet been published within the 6 month target this business year. The average time to produce conditional recommendations for the year is currently looking to 9.2 months, there is potential for this to reduce by the end of the FY. however unlikely to achieve 6 months.
Chart: Chart 12: Evidence generation plans developed for all new EVA products, with conditional recommendations​
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
Target for 23/24 out-turn | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
n/a | 100% | 100% | G
Expected to meet target and also clear backlog topics resulting from changes to the process.

## Slide 20: …that is usable and has a demonstrable impact
Chart: Chart 13: Resource impact products published at the point of guidance publication to support implementation
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
22/23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
100% | 90% | 100% | G
Expected to hit target.
Chart: Chart 14: 10% increase in the number of sessions on nice.org.uk
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual YTD | -0.014 | 0.008 | 0.039 | 0.058 | 0.0721 | 0.0829 | 0.0957 | 0.1 | 0.113 | 0.1019
Target for 23/24 out-turn | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
22/23 out-turn | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
3.5% growth | 10% growth | 10.19% | G
NICE.org has seen good growth in traffic year on year, after an initially slow start. Planned work on the content management system (CMS) and digital presence work should improve search engine performance. Though traffic growth slowed in January, this is attributed to normal fluctuations and not a cause of concern.
Chart: Chart 15: System priority topic areas with agreed measures of uptake reported
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0 | 0 | 0 | 0 | 0 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86
Target for 23/24 out-turn | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
0% | 80% | 86% | G
21 system priority topic areas have been agreed. Data extraction is complete for 19 topics. 12 out of the 14 topics related to Quality Standards have data extracted. 1 topic is paused and 1 is blocked related to issues with mental health data.

## Slide 21: While ensuring a financially sustainable organisation, with happy and well-supported staff, and effective communications and engagement
1 April 2023 to 31 January 2024

## Slide 22: Happy and well supported staff (Slide 1 of 3)
Chart: Chart 16: Sickness absence (proportion of WTE days reported as sickness)
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.0144 | 0.0176 | 0.0178 | 0.017 | 0.0183 | 0.0202 | 0.031 | 0.0332 | 0.0329 | 0.0289
Plan | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
Prior year | 0.0154 | 0.0131 | 0.0203 | 0.0204 | 0.02 | 0.0196 | 0.0191 | 0.0189 | 0.0188 | 0.0187 | 0.0188 | 0.0182
Average 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
1.89% | 2% | 2.35% | A
The sickness absence rate tends to increase in the autumn/winter months due to increased cold/flu related absence, but also Seasonal Affective disorder. There has also been an increase in long-tern sickness absence, and the management of change processes underway can also impact on sickness levels.
Chart: Chart 17: Rate of staff turnover
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.11 | 0.1128 | 0.1075 | 0.1067 | 0.1073 | 0.1013 | 0.1061 | 0.1075 | 0.1111 | 0.1059
Target | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
22/23 | 0.1153 | 0.1136 | 0.1189 | 0.1247 | 0.1229 | 0.1272 | 0.1277 | 0.1248 | 0.1244 | 0.125 | 0.1217 | 0.1097
March 2023 | YTD | Year-end forecast RAG status
10.97% | 10.76% | A
A new exit interview provider will provide better insight and analysis of reasons for leaving. The work should be completed with the exit questionnaire ready to go live by the end of Q4 (March 2024). ​In the interim, the People team prepared an online Exit questionnaire form which has been issued to all leavers since September.

## Slide 23: Happy and well supported staff (Slide 2 of 3)
Chart: Chart 18: Staff engagement scores remain good
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.68
Target | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
Column1
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
n/a | >60% | 68% | G
Engagement not measured during September’s and January’s pulse surveys.
Chart: Chart 19: 90% staff having completed an appraisal
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.0025 | 0.1089 | 0.6627 | 0.8222 | 0.8674 | 0.872 | 0.8848 | 0.8744 | 0.8773 | 0.8704
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
22/23 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87
Overall 2022 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
87% | 90% | 87.04% | A
Percentage will fluctuate month on month as the appraisals are logged on ESR and some members of staff with completed Appraisal leave the organisation.
Chart: Chart 20: 62% staff found their appraisal helpful
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.59
Target | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62
22/23 out-turn | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57
Overall 2022 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
57% | 62% | 59% | A
% has increased and it now falls only 1% outside of the "good zone" (60%). Issues identified in the feedback have been noted and actioned. Data on this metric will next be collected in April 2024.​

## Slide 24: Happy and well supported staff (Slide 3 of 3)
Chart: Chart 21: 20% increase in the proportion of ethnic minority staff at band 8a and above
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.1421 | 0.1448 | 0.1433 | 0.1464 | 0.1413 | 0.1421 | 0.1406 | 0.1444 | 0.1436 | 0.1455
Target for 23/24 out-turn | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667
22/23 out-turn | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
13.89% | 16.67% | 14.34% | A
Chart: Chart 22: 20% increase in the proportion of ethnic minority staff at band 7 and above
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.1664 | 0.1714 | 0.1733 | 0.1776 | 0.1727 | 0.1717 | 0.1695 | 0.1713 | 0.1736 | 0.1767
Target for 23/24 out-turn | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913
22/23 out-turn | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
15.94% | 19.13% | 17.23% | A
Both targets are anticipated by the end of the 2023/24 year. The recruitment process now requires a diverse interview panel for all band 7 and above roles and a new feedback form to ensure recruiting managers provide a clear rationale on why candidates have not been appointed and candidates receive good quality feedback; underpinned by increased availability of recruiting manager training.

## Slide 25: Effective communications and engagement (Slide 1 of 3)
Chart: Chart 23: 85% of lay people who complete exit surveys rate their experience of working with NICE as ‘good’ or ‘excellent’ ​
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0.67
Target for 23/24 out-turn | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85
22/23 out-turn | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
83% | 85% | 94% | G
January data based on 4 responses, with one respondent rating their experience as poor. Reasons for their experience are being investigated.
Chart: Chart 24: 10% increase in subscriber acquisitions on 3 corporate newsletters
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 59997 | 60796 | 61146 | 61437 | 62071
Target for 23/24 out-turn | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220
22/23 out-turn | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
57,473 | 63,220 | 61,437 | G
Between the start of the 2023/24 and January 2024, NICE News for Health and Social Care increased from 39,716 to 40,752; Update for Primary Care increased from 14,443 to 15,578 and NICE News for Life Sciences increased from 3,314 to 5,741. Note: data is YTD collected at the end of the reporting periods only.

## Slide 26: Effective communications and engagement (Slide 2 of 3)
Chart: Chart 25: Complaints acknowledged and responded to in 20 working days
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 1 | 1 | 1 | 100 | 1 | 100
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
22/23 | 1 | 1 | 1 | 1 | 1
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
100% | 80% | 100% | G
All complaints responded to within 20 working day deadline, and none currently under investigation by Ombudsman.
Chart: Chart 26: Freedom of Information requests responded to within 20 working days
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 1 | 0.94 | 1 | 0.88 | 1 | 0.96 | 0.95 | 1 | 1 | 1
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
22/23 | 0.9 | 1 | 0.91 | 0.89 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.89
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
98% | 90% | 97% | A
Currently expected to meet annual target.
Chart: Chart 27: Parliamentary Questions (PQs) contribution provided within requested time frame
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.92 | 1 | 1 | 1 | 0 | 0.93 | 0.93 | 1 | 1 | 1
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
22/23 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0.96 | 1 | 1
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
99% | 90% | 98% | G
No parliamentary questions (PQs) in August due to summer recess. Currently expected to meet target.

## Slide 27: Effective communications and engagement (slide 3 of 3)
The faecal immunochemical testing press release in July led to extensive media coverage which included our key message which is the main reason is why the
Chart: Chart 28: Proportion of media coverage of NICE that is positive
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.9 | 0.89 | 0.81 | 0.6 | 0.94 | 0.92 | 0.93 | 0.74 | 0.84
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
22/23 | 0.8 | 0.81 | 0.83 | 0.84 | 0.83 | 0.81 | 0.81 | 0.9 | 0.83 | 0.91 | 0.86 | 0.95
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
85% | 80% | 83% | G
Chart: Chart 29: Proportion of NICE generated news coverage that includes at least one key message
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.455 | 0.437 | 0.57 | 0.93 | 0.6 | 0.5 | 0.55 | 0.52 | 0.47
Target | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
22/23 | 0 | 0 | 0.54 | 0.54 | 0.57 | 0.63 | 0 | 0.55 | 0.52 | 0.58 | 0.56 | 0.54
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
56% | 60% | 55% | A
November saw the issue of the cystic fibrosis technology appraisal generate some negative comment, which continued into December. The media analysis company we use experienced a major service cyberattack in early February, which has delayed the January data.
The faecal immunochemical testing press release in July led to extensive media coverage which included our key message which is the main reason is why the figure is much higher than in previous months. The media analysis company we use experienced a major service cyberattack in early February, which has delayed the January data.

## Slide 28: Financial position as at 31st January 2024
Spend Category | Year to Date Budget £000 | Year to Date Actual £000 | Year to Date Variance £000 | Annual Budget £000 | Estimated Outturn Spend £000 | Estimated Outturn Variance £000
Pay | 49,101 | 48,298 | (803) | 59,246 | 57,889 | (1,357)
Non-pay | 18,020 | 17,301 | (719) | 23,909 | 22,151 | (1,758)
Income | (21,518) | (19,013) | 2,505 | (25,845) | (23,304) | 2,551
Total | 45,603 | 46,586 | 983 | 57,300 | 56,736 | (564)
Year to date overspend of £0.98m is primarily driven by under recovery against plan for technology appraisal (TA) income (£2.2m) and NICE Advice (£0.6m). This is partly offset by £0.8m underspend on pay (mainly in the Centre for Health Technology Evaluation; and Digital, Information and Technology, and Science, Evidence and Analytics Directorates) and a £0.7m underspend on non-pay (mainly due to uncommitted reserves, one-off VAT rebates relating to 2021-22 and 2022-23, lower than expected spend on committees, and DIT licences).
The forecast outturn is currently a £0.56m surplus (£0.45m surplus at M9). The forecast reflects the most likely outcome, with a worst-case scenario of £0.14m underspend and a best-case scenario of £0.97m underspend (see next slide).
Technology Appraisal forecast income has reduced since December from £10.5m to £10.4m.

## Slide 29: Forecast Outturn – risks and uncertainties – best-case worst-case scenarios ​
Uncertainties / Opportunities | Worst case FOT (£m) | Best case FOT (£m) | Comments
Month 10 FOT | (0.57) | (0.57) | Most likely based on current forecast assumptions
TA income | 0.10 | (0.10) | Assumed £10.4m in forecast but there’s a possibility this will move by year end
Restructure costs | 0.00 | (0.10) | Assumed £1.2m in the forecast. £960k remains to pay for redundancies expected in Q4
Manchester office rent review | 0.20 | 0.00 | Nil assumed in the forecast, review outstanding from Dec 2022, up to £200k pa expected
NICE Advice Range | 0.10 | 0.00 | Estimate - based on number of assumed slots being filled.
IFRS 16 Adjustment | 0.03 | 0.00 | Technical adjustment relating to change in lease (Manchester).
Cyber funding | 0.0 | (0.2) | NICE has been allocated £160k revenue funding to support improvements to cyber infrastructure, but due to the timing of this award it may not be possible to spend this funding. An additional £0.4m capital funding (not shown here) has been awarded, which may not be possible to spend either due to timing constraints.
Deficit / (Surplus) - Range | (0.14) | (0.97) | 

## Slide 30: Technology Appraisals – Month 10
TA Income YTD and Forecast
Month | Full cost recovery target (£000) | Actual income (£000) | (Surplus)/Deficit (£000)
April to Jan - 24 | 10,487 | 8,546 | 1,941
Feb-24 | 1,042 | 964 | 78
Mar-24 | 1,090 | 890 | 200
Total | 12,619 | 10,400 | 2,219
TA Income and Cost - YTD and Forecast
Forecast
The full year forecast income is £10.4m against an income target of £12.6m (82.5%). Some activity and topics that had been due to start before the end of the financial year have moved into 2024-25, primarily due to regulatory delays. There remains some uncertainty about milestones that will be achieved on a handful of topics and the forecast may reduce further.
The year-to-date TA position is a £1.9m under recovery of income against the full costs of the programme. The programme has recovered 81% of its year-to-date costs. The forecast under recovery for the full year programme is £2.2m.

## Slide 31: NICE Advice– FY 23-24 Forecast – Month 10
 |  |  |  | Year to Date Income | Year to Date Expenditure | Net | Income Forecast | Expenditure Forecast | Net
 |  |  |  | (£'000) | (£'000) | (£'000) | (£'000) | (£'000) | (£'000)
NA and NI only |  |  |  | (2,307) | 2,583 | 275 | (3,041) | 3,103 | 62
LST only |  |  |  | (220) | 686 | 466 | (254) | 770 | 517
Sub-total |  |  |  | (2,527) | 3,269 | 742 | (3,295) | 3,874 | 579
GIA allocation to LST |  |  |  | - | - | - | (517) | - | (517)
Aggregate NICE Advice forecast deficit |  |  |  | - | - | - | (3,812) | 3,874 | 62
Headlines
NICE Advice (NA) launched in November 2023 – performance reporting is now based on the combined function.
As at Month 10, the combined NA function is forecast to generate a £579k deficit for the year. This does not include the non-recurrent grant in aid (GIA) contribution to the Life Science Team’s (LST) funding for 2023-24 of £517k. There will be no GIA contribution in 2024-25.
This is based on a forecast income of £3,295k and expenditure of £3,874k. Of this forecast income, £19k is linked to currently vacant slots.
The forecast includes a £400k NA contribution for NICE intellectual property (IP).