## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
20/04 | 2020-09-16 | 20/085 | Review the equalities implications of virtual recruitment interviews. | JH | 2021-04-01 | HR have undertaken a scoping exercise around the potential equalities impact of virtual recruitment, and have also consulted with fellow ALBs and other organisations. No substantial research or data identified around this topic, though HR will continue to seek and keep abreast of material as it emerges. In light of the current lack of data about the equality impacts of virtual recruitment, an external EDI consultant has been asked to conduct an EIA on our current process and practices. | Closed | 2021-05-19
20/05 | 2020-09-16 | 20/087 | Revised digital workplace business case to be brought to the Board following the work to: • clarify the sequencing of the transformation activities and how this can de-risk the investment • scrutinise the costs and review the use of external expertise to ensure this offers value for money, taking account of external benchmarking • clarify the centrality of the programme to the NICE Connect vision • further articulate the scale of the business process transformation and cultural change it will introduce for NICE. | AT | 2021-04-01 | The due diligence of the business case presented in September was completed. This led to a recommendation to initiate some of the work from the original 'foundational phase' in early 2021 in order to bring an updated business case back to the Board in April 2021. A 'case for change' paper was presented to the Board in April 2021 - feedback was received from the Board which was incorporated in the full business case presented for sign off at the May Board meeting. | Closed | 2021-05-19
20/12 | 2020-11-18 | 20/108 | Board to receive further information in January on the review of the recruitment process with a focus on increasing the diversity of appointees. | JH | 2021-04-01 | EDI action plan was signed off by ET in February and shared with the Board in May. It includes a comprehensive programme of interventions which will support our aspiration to increase the diversity of appointees. Since then we have conducted an audit of our recruitment process, and introduced changes, including a refreshed hiring manager ‘checklist’ which builds in greater manager accountability and corporate oversight into our recruitment process. A key priority is the delivery of a new training offer for hiring managers and the establishment of diverse panels (initially for Band 8 and above, with an aspiration to extend). These are both currently in planning stage, for roll out end Q1/Q2. We have also subscribed to Vercida, a specialist website which helps organisations to implement a robust EDI approach to recruitment (through advice, strategic advertising, data analytics etc). | Closed | 2021-05-19
20/13 | 2020-11-18 | 20/109 | Board's implementation 'deep dive' in December to consider the scope to look at whether there are consistent themes across the impact reports. | JR | 2021-05-01 | Consideration of whether there are consistent themes across impact reports is complete and the findings are reported in the May H&SC Board report. This will also feed into the review of the implementation strategy. | Closed | 2021-05-19
21/01 | 2021-01-27 | 21/007 | Board to receive further information on the actions to address the vacancies. | JH | 2021-03-01 | Summary on workforce planning included in March Resources report. Proposal for creating a flexible and sustainable resourcing model considered by ET in April with approval to bring in a Workforce Planning Business Partner for 12 months together with a number of other initiatives designed to support recruitment processes and an ability to recruit to hard to fill roles. ET monitoring vacancies every 2 weeks. | Closed | 2021-05-19
21/02 | 2021-01-27 | 21/009 | Board to receive further information on the measures that will be used to quantify the success of the Innovative Licensing and Access Pathway. | FG | 2021-07-01 | Measures of success for ILAP currently being developed by MHRA, NICE and SMC, and will be reviewed at next joint ILAP steering group. Success measures will be shared with the Board in the life sciences strategic pillar report in July | Open | n/a
21/07 | 2021-03-24 | 21/023 | Board to be advised how the planned targets for 2021/22 relate to the original plan for 2020/21 and the revised plan agreed in May 2020. | GL | 2021-04-01 | Information provided to April Board strategy meeting. | Closed | 2021-05-19
21/08 | 2021-03-24 | 21/023 | Board to receive an update on the work to develop business and marketing strategies for NICE International, along with a progress update on NICE International’s work more generally. | MB | 2021-07-01 | Scheduled for the July Board meeting. | Open | n/a
21/09 | 2021-03-24 | 21/023 | JG to find out if it is possible to gauge the level of international interest in NICE’s COVID-19 guidelines. | JG | 2021-05-01 | Mar 2020-Apr 2021:117 countries accounted for 29% of the total 670,430 Covid page views | Closed | 2021-05-19
21/10 | 2021-03-24 | 21/025 | MB to consider whether any further actions are required to ensure stakeholders have sufficient opportunity to comment on the methods and process manual given the consultation is due to coincide with the summer holiday period. | MB | 2021-05-01 | We cannot extend the consultation period beyond the 6 week period already planned. If individual organisations do require more time in order to respond, we can consider a short extension to the consultation end date. We ask organisations to reach out early so that we can build in additional time and resource to review their comments and respond accordingly. | Closed | 2021-05-19
21/11 | 2021-03-24 | 21/027 | Board to discuss further the proposal to select health inequalities as the first NICE Listens topic or whether another topic is more appropriate. | FG | 2021-04-01 | Agreed with the Chairman to continue to pursue health inequalities as the initial topic - but to engage the Board in the work to pick subsequent topics. | Closed | 2021-05-19
21/12 | 2021-03-24 | 21/027 | Board to receive further information on the work plan for the Office for Digital Health. | FG | 2021-06-01 | Workshop to explore digital work plan with Board members being set up for May/June. | Open | n/a
21/13 | 2021-03-24 | 21/028 | Findings of the review of the current local use and perceptions of Quality Standards across the health and care system to be shared with the Board for information. | JR | 2021-04-01 | Sent to the Board by email on 21/4/21. | Closed | 2021-05-19
21/14 | 2021-03-24 | 21/029 | Further information on the revised approach to budget-setting and monitoring for the upcoming year, that will seek to avoid a significant underspend to be provided to the Board when it is asked to approve the budget, along with information on the savings arising from virtual working. | JH | 2021-05-01 | Further information on the approach to budget setting and monitoring was presented to morning session of May Board. Information on savings arising in 2020/21 from virtual working included in May People and Resources report. | Closed | 2021-05-19
21/15 | 2021-03-24 | 21/032 | Revised Charter to be published on the website after the strategy launch, subject to strengthening the references to NICE's work to support integration of health and social care. | JG | 2021-04-01 | Completed - refreshed strategy live on the website. | Closed | 2021-05-19
21/17 | 2021-03-24 | 21/033 | Executive Team to consider further the implications of applying the proposed accompanying changes to the policy for advisory committees and agree whether to update this policy as proposed in the Board paper. | GL | 2021-05-01 | Confirmed that there were no issues in making the proposed changes and the revised policy was issued. | Closed | 2021-05-19
21/18 | 2021-03-24 | 21/034 | Responses to the questions from the audience to be provided in the papers for the next Board meeting. | DC | 2021-05-01 | Responses included with the Board papers. | Closed | 2021-05-19