## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
21/38 | 2021-11-17 | 5 | Board to receive further information on the scope to utilise the prototype equity impact calculator developed with the University of York and the outcome of the current review of NICE’s approach to addressing health inequalities. | JR | 2022-03-01 | Further information to be included with paper on health inequalities to March 2022 public Board meeting. | Open | n/a
21/39 | 2021-11-17 | 6 | Outcome of the 2021/22 business plan prioritisation to be circulated to the Board. | JH | 2021-12-01 | Circulated via email on 3 December 2021. | Closed | 2022-01-19
21/40 | 2021-11-17 | 7 | International strategy to be amended to strengthen the reference to NICE contributing to global health priorities and projects that could be undertaken collaboratively to deliver NICE’s strategy. | MB | 2021-12-01 | Strategy updated and shared with the CEO. A summary of the international strategy is currently being designed prior to publication. | Closed | 2022-01-19
21/41 | 2021-11-17 | 9 | Further information to be provided to the Board on how the transferring staff from the NGA and NGC will support delivery of the new guidelines operating model, and the impact on the relationships with the two Royal Colleges. | PC | 2022-04-01 | The TUPE process is being managed by a programme board. New operating models are being explored for the transition to topic suites, supported by centralised centres of excellence. | Open | n/a