## Public board meeting action log
Public board action log
Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
2020-07-15 | 20/060 | Board to receive further update on the outcome of the pilot evaluation of digital health technologies. | MB/HK | 2020-11-01 | Scheduled for the November Board meeting. | Closed | 2020-11-18
2020-07-15 | 20/065 | Follow-up with NHSX the bid for funding to develop methods for the evaluation of technologies with embedded AI. | GL | TBC | This has been followed up but the timing for a further bid has been put back to later in the year. Funding has also be sought through the CSR process. | Open
2020-07-15 | 20/070 | The scope for NICE to tackle health inequalities to be explored further as part of the current work to develop a 5 year strategy, and consideration given to seeking an external view on whether NICE could do more in this area. | GL/PC | 2020-12-01 | NICE is currently considering its role in public health in a changing public health system alongside the current work to develop a 5 year strategy. In addition, we are exploring the contribution NICE can make to tackle health inequalities through our guidance outputs. | Open
2020-07-15 | 20/072 | Audit & Risk Committee's terms of reference to be amended to include provision for an external member. Terms and conditions for the external member to be finalised, if the position is required following the outcome of the NED appointments. | SN | 2021-01-01 | Amendments to the terms of reference drafted. Issue now on hold pending outcome of NED recruitment. | Open
2020-09-16 | 20/083 | Statement on the impact on NICE of the end of the transition agreement to be shared with the Board prior to publication on the NICE website. | JG | 2020-11-01 | This has been circulated to Board members. | Closed | 2020-11-18
2020-09-16 | 20/084 | Board to receive an update on the engagement with the Association of Directors of Adult Social Services in England and Skills for Care. | JR | 2020-11-01 | Engagement is ongoing with a number of colabarative projects. For example we are working with Skills for Care, the Local Government Association and the Association of Directors of Adult Social Services on a new national working group to promote and support wellbeing across the social care workforce. | Closed | 2020-11-18
2020-09-16 | 20/085 | Review the equalities implications of virtual recruitment interviews. | JH | 2020-12-01 | Review of evidence as set out in the equalities report indicates that virtual recruitment remains a challenge for the equalities agenda. Plans to address this will be set out following discussion of the equalities objectives. | Open
2020-09-16 | 20/087 | Revised digital workplace business case to be brought to the Board following the work to: • clarify the sequencing of the transformation activities and how this can de-risk the investment • scrutinise the costs and review the use of external expertise to ensure this offers value for money, taking account of external benchmarking • clarify the centrality of the programme to the NICE Connect vision • further articulate the scale of the business process transformation and cultural change it will introduce for NICE. | AT | 2020-12-01 | Work is ongoing internally to review and update the business case including the review and scrutiny of external expertise costs. Aim is to present an update to the December Board strategy meeting. | Open
2020-09-16 | 20/088 | IMMDS review's findings to be used as an opportunity to work with partners to reinforce the importance of NICE’s interventional procedures guidance. | JR/KH | 2020-11-01 | An update on NICE's patient safety activity is presented at the November Board meeting. | Closed | 2020-11-18
2020-09-16 | 20/088 | NICE's response to the IMMDS review to be publicised on the website. | JG | 2020-11-01 | NICE's response will be published on the website and a blog from K Harris is being produced. | Open