## Slide 1: SUSPECTED CANCER: RECOGNITION AND REFERRAL IMPLEMENTATION EVENT LSC SCN Neil Smith Lynn Scott Juliette Brookfield 4.3.16

## Slide 2
Chart: 
| Demand modelling | Pathway redesign | Creating referral forms | Access to urgent investigations | Patient engagement | Financial and workforce planning | GP education | Capacity increase
 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Slide 4: Demand modelling assumptions
Natural growth trajectory
Demographic growth- numbers/ aging
Awareness campaigns
Specific NICE changes
No science, no guidance
Best estimates BUT our “educated” guesses are being used nationally

## Slide 5
Chart: 2WR into EAST LANCASHIRE NHS HOSPITALS TRUST - estimated
| Baseline | 2016-17 estimated | 2017-18 estimated | 2018-19 estimated | 2019-20 estimated | 2020-21 estimated
Brain | 1 | 1 | 1 | 1 | 1 | 1
Breast | 4200 | 4326 | 4456 | 4590 | 4705 | 4799
Colorectal | 2508 | 3075 | 3770 | 4168 | 4608 | 5094
Gynaecology | 1429 | 1472 | 1516 | 1562 | 1601 | 1641
Haematology | 96 | 98 | 100 | 102 | 104 | 106
Head and Neck | 1832 | 2173 | 2577 | 2797 | 3036 | 3295
Lung | 612 | 677 | 748 | 797 | 849 | 904
Other | 38 | 39 | 40 | 41 | 42 | 43
Paediatric | 105 | 111 | 117 | 123 | 126 | 129
Sarcoma | 20 | 20 | 20 | 20 | 20 | 20
Skin | 2446 | 2704 | 2989 | 3304 | 3553 | 3821
Upper GI | 2214 | 2781 | 3494 | 4214 | 4870 | 5384

## Slide 6
Chart: Projected Increase in Diagnostic Demand in ELHT
| Endoscopies | Angiography | CT | Fluoroscopy | Mammography | MRI | Nuclear Medicine | Obstetrics | Radiology | Ultrasound
Baseline | 4592 | 33 | 3446 | 349 | 2451 | 839 | 764 | 60 | 3918 | 7247
2016-17 | 5638 | 36 | 4007 | 415 | 2533 | 951 | 846 | 64 | 4524 | 7685
2017-18 | 6932 | 42 | 4676 | 496 | 2621 | 1084 | 941 | 68 | 5248 | 8178
2018-19 | 7970 | 47 | 5171 | 561 | 2710 | 1182 | 1016 | 72 | 5805 | 8607
2019-20 | 8981 | 51 | 5649 | 624 | 2785 | 1274 | 1086 | 75 | 6340 | 8991
2020-21 | 9905 | 55 | 6125 | 680 | 2847 | 1367 | 1152 | 79 | 6858 | 9347

## Slide 7
Chart: Estimated total cost
| Baseline | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21
Estimated total cost | 5778358.8 | 6692376 | 7797478.3 | 8669754.5 | 9509205.1 | 10301301.7

## Slide 8
Next Steps
Seek CCG agreement and support for additional resources.
Seek CCG agreement with the potential use of other providers and a primary care model
Sense check growth assumptions with other localities.
Further refine modelling to include potential impacts on pathology, histology and haematology.
Further financial modelling to reflect updated information.
ELHT capacity gap analysis.
Develop commissioning plans to ensure sufficient capacity within the healthcare system.
Ensure contracting/ quality arrangements support implementation.
Finalise plan for full implementation of NICE Guidance.
Agree data set/metrics to support robust monitoring, demonstrating service improvement in relation to clinical outcomes and patient experience.
Develop and agree tool for monitoring patient experience and satisfaction.
Consider any emerging service redesign issues.
Consider potential workforce implications.

## Slide 9: Provider Actions – What we have done to date
Lots of meetings with CCG reps to redesign the 2ww proformas to meet the revised NICE guidance
Meetings held between Macmillan GP and all the hospital MDT Consultant leads to discuss their particular proforma
Established 2 working groups – an external group with CCG and CSU representation (2ww Task & Finish Group) and internal group (2ww Implementation Group) – meeting monthly subsequent to the new guidelines
‘Sub-meetings’ ++ with key stakeholder areas such as Information Team, Radiology Manager and Histopathology Manager

## Slide 10: Roll out
Phase 1
Breast (2ww and separate proforma for breast symptomatic referrals)
Upper GI / Iron Deficiency Anaemia/ Jaundice
Head & Neck
Haematology
Gynaecology
Bone
Sarcoma
Brain
Phase 2
Lung
Urology
Skin
No plan yet – Colorectal due to need to address endoscopy capacity first

## Slide 11: Operational Challenges
Change in pathway – for example ultrasound now before OPA in gynae (GPs make referral for u/sound at time of emailing a 2ww proforma) – has required changes in processing appointment allocation for the Trust booking team
Change in pathway – paediatrics – some conditions to be seen within 48 hours (Brain & CNS/Leukaemia/Lymphoma (inc H&N if under 16 years)/Bone sarcoma/Soft tissue sarcoma/Neuroblastoma/Retinoblastoma/Wilms’ tumour
Re-issue of 2ww proformas to dentists – dentists not commissioned by our CCG so our CCG had to make separate contact with our local NHS England representative
All proformas needed re-writing,(keeping everyone happy) edited into EMIS format, sent to 87 practices, imported into document templates with old ones deactivated then each G.P. has to find each form individually.

## Slide 12: Operational Challenges
Some local pathways agreed – eg Iron Deficiency anaemia
GPs understanding the new referral pathways – requiring micromanagement in some tumour groups – particularly HPB and Upper GI/Iron Deficiency Anaemia referrals
Paediatrics – still work in progress to ‘get right’ – needing micromanagement
Upper GI – still work in progress to ‘get right’: straight to scope but also OPA if GP indicates abdominal mass
Recognition more time required for clerks in the booking team – discussion with finance teams to provide funding for 2 additional band 3 staff
Skin – concern from the Consultants that the 2ww process will ‘flood the system’ due the bcc’s

## Slide 13: Example of a revised pathway
OVARIAN PATHWAY
Patient presents with symptoms that would suggest ovarian cancer
GP Requests CA125
If CA125 > 30IU/ml
GP to request ultrasound scan as red cross/category 7 and completes 2WW proforma and e-mail to Booking Centre
Radiology to book ultrasound scan within 7 days and booking team to ensure OPD made ASAP following ultrasound scan
Patient seen in the out-patient clinic and informed of findings of ultrasound scan
0
7
14

## Slide 14: Operational Challenges
Decision of how to record clock stop against the 14 day target is the absence of any formal DoH revised guidance
Contacted Cancer Waits re a u/s scan ‘stopping the clock’ – received email back to confirm this. Now work being undertaken by CCG re possibly putting this into a contract variation

## Slide 15: Next Steps
Micromanagement of the pathways – ongoing -
still a lot to do
Refine system for monitoring 2ww referrals to see if the actual number of referrals increases as per the predictions
Release and Implement tumour groups in Phase 2
Wider project addressing endoscopy capacity for the predicted increase in colorectal referrals
Plan/Coordinate process for NICE guidelines that recommend a GP does a diagnostic test before a 2WW referral (our Blue Chart – v our Red Chart!)
Uncertainty about the NICE recommendation on ‘refer for FOB’ – not offered locally
Continue our work so that we can plan/implement the National Cancer Strategy – 95% cancer patients to be diagnosed by day 28 (2020)