Pennine Lancashire

Future Demand Modelling for Cancer Services, in response to

NICE Cancer Guidelines 2015

- Introduction:

ImprovingOutcomes:AStrategyforCancer (IOSC)waspublishedin2011, withitsmainfocusbeingtheimprovement ofcancersurvivalthroughearlierdiagnosisofcancerandimprovedaccesstothebestpossibletreatment.SincethepublicationofIOSC,there hasbeenacontinuingfocusonearlydiagnosisasthekeytoimprovingcanceroutcomes.

Suspected cancer 2 week wait referrals (2WR) are already demonstrating growth year on year, with an average growth into East Lancashire Hospitals NHS Trust (ELHT) over the last 4 years of 11.2% per year or 2.8% per quarter. This includes demographic growth and the impact of Be Clear on Cancer (BCOC) campaigns. This is illustrated in chart 1 below.

Chart 1

The 2015 changes to NICE Cancer guidance will have the effect of further increasing activity across most specialties.  An overview of the key changes is detailed below:

- Threshold level of risk reduced from positive predictive value (PPV) of 5% to 3%

- Layout by site of possible cancer and symptom

- Direct access investigations including oesophago-gastro-duodenoscopy (OGD), ultrasound (US), computed tomography (CT), faecal occult blood (FOB)

- Strength of recommendation –‘offer’ versus‘consider’

- Timings very urgent e.g. 48 hours for children

- Patient information, support and safety netting

In addition, one focus of the document ‘Achieving World Class Cancer Outcomes’, published in 2015,is early diagnosis, with the aim of achieving the target of ‘ 95%

patients  receiving a definitive diagnosis (or cancer excluded) within 28 days’ by 2020, again contributing to a further potential increase both in demand for diagnostics  and the required urgent access and reporting.

- Thecasefor a Pennine Lancashire approachtocapacityanddemandmodelling

forcancerservices

As commissionersandproviders,itis essentialthat theimpacts ofthe above Cancer NICE Guidance and National Strategy, as well as,demographicchange,publicawareness and screeningprogrammesarefactoredintofutureserviceplanning.Thiswillbeintegralinensuringtheprovisionof sustainable cancer serviceswhichdeliverthebest access, outcomes and patient experience forpeopleaffectedbycancerin Pennine Lancashire. Duetothecomplexityofmanycancer pathwaysacross Pennine Lancashire, it isrecognisedthatundertakingthis pieceofworkacross the Pennine Lancashirefootprintwillsupport ongoing workto standardiseandimprovecancer servicesacross thearea whilst at the same time reducing inequalities in cancer service provision.

#### Aim

To quantify current and projected demand and capacity for assessmentanddiagnostic    services requiredacrossPennine Lancashire,atpathwayandtestlevel.  This will supportcommissionersandprovidersinplanningforincreasedsuspectedcancerreferralsanddiagnosticdemand,asaresultofthenationaldrivetowardsearlierdiagnosis.  It will also highlight thelikelyactivityandcostimplicationsofpossibledemandshifts.

#### Objectives

#### Phase 1:

- To establish structures/define governance arrangements to support delivery of the above aim.

- To quantify/estimate the potential increase in activity across the cancer pathway of changing demand.

- To quantify/estimate the potential impact on individual tumour sites.

- To quantify/estimate the cost implications of changing demand

  - Phase 2:

- To identify any gaps in capacity.

- To seek assurance from provider re their ability to deliver increased capacity.

- To agree and implement required commissioning and delivery plans to ensure sufficient capacity within the healthcare system as a whole (considering other providers).

- To ensure financial, contractual and quality arrangements are in place to support agreed strategy.

- To agree data set/metrics to support robust monitoring, demonstrating service improvement.

- To develop and agree tool for monitoring patient experience and satisfaction.

4.3Phase 3

Toscopepotentialfutureservicemodelstodeliversustainablecancerservicesacross Pennine Lancashire, recommending new service models which may be implemented as standard across Pennine Lancashire (e.g. direct access diagnostics, expansion of one stop models).

- To quantify the workforce/training implications across the cancer pathway as a result of changing demand.

- Process:

- Engagedwithcliniciansacrosscommissioning,primary,secondaryandtertiarycareorganisationsto assess the impact of potential increases/changes indemandforcancer and diagnostic servicesover thenext5years.

- Established a NICE Task & Finish group which meets monthly, comprising commissioner/provider/contracting/quality representation both clinical and management with robust governance arrangements to oversee the delivery of NICE Guidance and development of adequate capacity across the healthcare system.

- Ongoing development of plans for phased implementation of NICE Guidance.

6.0	Demand modelling assumptions:

The data on which the demand modelling is based is ELHT data only.  In 2014/15 East Lancashire Clinical Commissioning Group (ELCCG) referred 7.92% and Blackburn with Darwen Clinical Commissioning Group (BwD CCG) referred 1.97% of patients to providers other than ELHT,accounting for 6.21% of all Pennine Lancs 2 week wait referrals.

The following assumptions have been made in the calculation of potential increase in demand:

- Demographic growth – 0.5% demographic growth was applied to each of the tumour groups.

- Current growth trends–  two methods of reviewing growth trends were considered – a 12 month rolling average and an average annual growth over 4 years. These often produced very different information so local knowledge was also applied.

- Impact of NICE guidance – the guidance to support NICE implementation indicated that there would be significant increased demand in the following tumour groups:

- Colorectal

- Lung

- Upper GI

7.0	Estimated increase in demand across all tumour sites:

Based on the above, the potential increases in demand in each of the individual tumour sites have been estimated as below in chart 2:

Chart 2

Based on the above information, the cancer pathways estimated to have the largest numerical growth in two week wait referrals include upper gastrointestinal cancer, head and neck, colorectal, skin and urology, and are detailed below in chart 3:

Chart 3

When factoring in existing baseline growth, and expected referral increases as a result of public health campaigns and changing NICE guidance, there are forecast to be approximately 27,352 two week wait referrals into ELHT by 2020/21. This represents an additional 8,285 referrals when compared to baseline.

The new NICE Guidance will also impact significantly on the demand for diagnostics. Chart 4 identifies the potential impact by test.  However, it should be noted that histology, pathology and haematology impacts are in the process of assessment and as such are not included in this table.

Chart 4

8.0Financial Appraisal

Financial appraisal of the potential cost implications have been undertaken based on existing information and assumptions (detailed information available if required).  This will need further refinement once all information is available.  Chart 5, below demonstrates the estimated year on year cost, with an additional approximate cost of one million pounds annually across Pennine Lancashire based on current tariff.

Chart 5

Based on a 70:30 apportionment of costs across Pennine Lancashire, this would be approximately, per annum:

- East Lancashire CCG:		£700,000.00

- Blackburn with Darwen CCG:	£300,000.00

Chart 6 below provides a detailed breakdown of potential costs over the next five years:

Chart 6

| Tariff | Baseline | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 |
| --- | --- | --- | --- | --- | --- | --- |
| Two week rule referrals |  |  |  |  |  |  |
| First outpatient appointments | £ 2,457,631 | £ 2,735,090 | £ 3,060,771 | £ 3,311,303 | £ 3,548,731 | £ 3,785,262 |
| Endoscopies | £ 2,296,000 | £ 2,819,000 | £ 3,466,000 | £ 3,985,000 | £ 4,490,500 | £ 4,952,500 |
| Angiography | £ - | £ - | £ - | £ - | £ - | £ - |
| CT | £ 275,680 | £ 320,560 | £ 374,080 | £ 413,680 | £ 451,920 | £ 490,000 |
| Fluoroscopy | £ - | £ - | £ - | £ - | £ - | £ - |
| Mammography | £ - | £ - | £ - | £ - | £ - | £ - |
| MRI | £ 107,008 | £ 121,728 | £ 138,752 | £ 151,296 | £ 163,072 | £ 174,976 |
| Nuclear Medicine | £ 323,172 | £ 357,858 | £ 398,043 | £ 429,768 | £ 459,378 | £ 487,296 |
| Obstetrics | £ - | £ - | £ - | £ - | £ - | £ - |
| Radiology | £ - | £ - | £ - | £ - | £ - | £ - |
| Ultrasound | £318,868 | £ 338,140 | £ 359,832 | £ 378,708 | £ 395,604 | £ 411,268 |
| Total Radiology | £1,024,728 | £1,138,286 | £1,270,707 | £1,373,452 | £1,469,974 | £1,563,540 |
| Total | £5,778,359 | £6,692,376 | £7,797,478 | £8,669,755 | £9,509,205 | £10,301,302 |
| Movement from previous year |  | £914,017 | £1,105,102 | £872,276 | £839,451 | £792,097 |
|  |  | 15.8% | 16.5% | 11.2% | 9.7% | 8.3% |

9.0Nextsteps:

- Seek CCG agreement and support for additional resources.

- Seek CCG agreement with the potential use of other providers and a primary care model

- Sense check growth assumptions with other localities.

- Further refine modelling to include potential impacts on pathology,histology and haematology.

- Further financial modelling to reflect updated information.

- ELHT capacity gap analysis.

- Develop commissioning plans to ensure sufficient capacity within the healthcare system.

- Ensure contracting/ quality arrangements support implementation.

- Finalise plan for full implementation of NICE Guidance.

- Agree data set/metrics to support robust monitoring, demonstrating service improvement in relation to clinical outcomes and patient experience.

- Develop and agree tool for monitoring patient experience and satisfaction.

- Consider any emerging service redesign issues.

- Consider potential workforce implications.

Throughout this process there must be a continued focus on achieving allCancer Waiting Time Targets.

10.0	Conclusion

From the above it is evident that the vision and direction of travel for cancer services as a whole is focused on early diagnosis, improving outcomes and improving patient experience.  Theestimation of the increase in demand on services clearly provides a challenge for both commissioners and providers of cancer services.  As such, it will require the continued collaborative working across Pennine Lancashire, extending to the wider Lancashire footprint as and when required, to achieve the quality and targets set out in the above documents and also clearly mandated in 2016/2017 – 2020/2021 Delivering the Forward View: NHS Planning Guidance.

11.0	Recommendations

11.1 To receive the report and consider the impact on cancer services across Pennine Lancashire.

11.2  To support the additional resources to implement the proposals within the report.

11.3 To support continued collaborative working across Pennine Lancashire and the wider Lancashire footprint.

Lynn Scott

Service Redesign Manager – Cancer Lead, East Lancs and BwD CCGs

Dr Neil Smith

Macmillan GP, Cancer Lead, East Lancs and BwD CCGs

3rd February 2016