## Slide 1
Asthma - diagnosis and monitoring guideline: primary care implementation feasibility project update
Adoption & Impact Programme, NICE:
Sally Chisholm, Programme Director
Jennifer Watts, Associate Director
Heather Stephens, Project lead
3rd June 2016

## Slide 2: Attendees
Association for Respiratory Technology & Physiology
Asthma UK
British Paediatric Respiratory Society
British Thoracic Society
Royal College of Physicians
Royal College of GPs
Royal College of Nursing

## Slide 3: Who we are
The Adoption & Impact programme is part of the Health & Social Care directorate and consists of 3 teams:
  Adoption and Impact
  Resource Impact Assessment
  Implementation Support
The teams work to support the effective implementation of NICE guidance.

## Slide 4: Adoption Team
Work with NHS and social care organisations to implement medical technologies and diagnostic tests
Develop documentation to support the wider system in the adoption of the technologies

## Slide 5: Impact Team
Data and analytical support:
Support guidance development teams by providing data.
Measuring the uptake of NICE guidance:
Innovation scorecard
Uptake database
Impact report

## Slide 6: Background
January – March 2015: Asthma - diagnosis and monitoring: guideline consultation
August 2015: guideline delayed to allow additional time to work with healthcare professionals in asthma care to make sure the recommendations can be introduced effectively and efficiently
September – December 2015: feasibility project planning and internal approvals
January – February 2016: site recruitment and selection
Notes: .

## Slide 7: Project aims and objectives
To assess the impact and feasibility of implementing, into primary care, 2 of the objective tests recommended in the different diagnostic algorithms of the proposed guideline:
  spirometry
  fractional exhaled nitric oxide (FeNO)
To allow the project sites to test implementation, in a real world setting, with no external influence and report the benefits and challenges they experience

## Slide 8: Timeline
Date | Milestone
2 May 16: | project start
31 Oct 16: | project completion
21 Dec 16: | feedback meeting
Jan 17: | final report to CCP / GDG

## Slide 9: Site recruitment
Dedicated asthma diagnosis and monitoring feasibility project webpage on the NICE website
NICE Update for Primary Care newsletter
NICE GP newsletter
NICE Twitter page
NICE implementation field team CCG contacts
PCRS and Asthma UK member update
Requested NHS England and RCGP to promote

## Slide 10: Expressions of interest
78 EoI received before closing date
69 single and 9 multi-site:
  North East (4)
  North West (17)
  Yorkshire and Humber (6)
  East Midlands (5)
  West Midlands (9)
  East of England (4)
  London (3)
  South West (24)
  South East (6)

## Slide 11: Site selection
Size of the practice (patient numbers)
Geographical location (across England)
Percentage of patients with asthma diagnosis
Current care pathway for diagnosis
Registered patient characteristics (deprivation scores, ethnicity and age)
Full application and no conflict of interest
Ability to provide retrospective data

## Slide 12: Project site characteristics
Site | Location | Surgeries | Registered Persons | % < 18 years | % 65+ years | Asthma % | Deprivation decile | % non-white ethnic group
1 | North East | 1 | 3074 | 16.7 | 18.1 | 8.7 | 5 | 1.4
2 | North West | 2 | 10,900 | 18.3 | 3.6 | 4.3 | 2 | 46.5
3 | West Midlands | 1 | 24,000 | 21.9 | 17.4 | 6.3 | 4 | 29.7
4 | East Midlands | 1 | 14,098 | 22 | 18.2 | 6.3 | 6 | 6.6
5 | East of England | 4 | 17,500 | 15.9 | 29.1 | 6.5 | 6 | 1.1
6 | London | 1 | 7,300 | 15.4 | 5.8 | 3.6 | 6 | 36.0
7 | South West | 4 | 19,000 | 18.5 | 17.7 | 6.1 | 6 | 2.5

## Slide 13: Support to sites
£3,000 per project site to facilitate data collection
Funding and signposting to spirometry training if required
Choice of NICE recommended FeNO device and all required consumables during project at no charge from manufacturer

## Slide 14: Project initiation
Structured phone interviews
Site visits
  information exchange
  care pathway mapping
  data collection agreement and methods
  training requirements

## Slide 15: Project monitoring
Monthly semi structured phone interviews with key members of the site implementation team to gather qualitative measures required
Monthly quantitative data submission
End of project face to face meeting with Asthma feasibility project team

## Slide 16: Baseline data
Presentation
Date
Age
Diagnosis
Final diagnosis (asthma / other / uncertain)
Date of asthma diagnosis
Time spent on diagnosis appointments
Number of appointments to diagnosis
Place of diagnosis (primary care / secondary care OPD / secondary care admission)

## Slide 17: Quantitative data (1)
Presentation
Date
Age
Appointment duration (minutes)
Spirometry
Spirometry date
Appointment duration (minutes)
Spirometry result (obstructive / normal)
Number of filters used
Staff performing spirometry (HCA / nurse / GP)
Staff interpreting spirometry (HCA / nurse / GP)

## Slide 18: Quantitative data (2)
Bronchodilator reversibility (BDR)
BDR test date
Appointment duration (minutes)
BDR result (positive / negative / N/A)
Number of filters used
Staff performing BDR (HCA / nurse / GP)
Staff interpreting BDR (HCA / nurse / GP)
FeNO
FeNO date
Appointment duration (minutes)
FeNo result (positive / negative / N/A)
Number of filters used
Staff performing FeNo (HCA / nurse / GP)
Staff interpreting FeNo (HCA / nurse / GP)

## Slide 19: Quantitative data (3)
Peak flow variability
Peak flow variability monitored (yes / no)
Peak flow result (positive / negative / N/A)
Direct bronchial challenge
Date referred for direct bronchial challenge test
Date of test
Bronchial challenge test result (positive / negative / N/A)
Other onward referral
Other onward referral (yes / no)
Referred to

## Slide 20: Quantitative data (4)
Diagnosis
Date of diagnosis
Diagnosis (asthma / other / uncertain)
Diagnosing clinician (site nurse / site GP / secondary care)
No. of practice appointments to reach diagnosis

## Slide 21: Qualitative data (1)
Training
Estimated time to reach competency in spirometry
Estimated time to reach competency in FeNO
Care pathway
Changes to the care pathway to accommodate the guideline
Facilities / clinic capacity requirements
Staff compliance in following the pathway
Patient feedback
Spirometry
FeNO

## Slide 22: Qualitative data (2)
Implementation barriers / levers
Training
Confidence in results
Impact on workload
Undertaking testing
Future plans
Equipment
Guideline implementation

## Slide 23: Questions and discussion https://www.nice.org.uk/about/nice-communities/general-practice/asthma-primary-care-project