## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
22/04 | 2022-03-17 | 8 | Board to be updated when the health inequalities oversight group has confirmed any changes to NICE’s approach in light of the NICE Listens recommendations. | JR | 2022-12-01 | NICE Listens recommendations complemented those from the external consultant who carried out an engagement exercise with strategic partners therefore recommendations have been incorporated into the health inequalities priorities for 2022/23. A progress update against the priorities has been presented to the December public board meeting. | Closed | 2022-12-16
22/06 | 2022-05-25 | 5 | Board to receive an update on hybrid working when qualitative and quantitative data is available on whether the working arrangements both provide flexibility for staff and support the delivery of the transformation programme. | NG | 2023-03-01 | Update to be provided in the new year. We will be recommencing hybrid working contract discussions with staff once the permanent CPO starts. | Open | n/a
22/10 | 2022-05-25 | 6 | Board to receive an update on the long-term funding mechanism for ILAP at a suitable point in the future. | HK | 2022-12-01 | Update provided to the December Board seminar. | Closed | 2022-12-16
22/15 | 2022-05-25 | 8 | Board to receive information on the results of phishing simulations undertaken at NICE. | AT | 2022-10-01 | An update on phishing simulation was provided to the Audit and Risk Committee. | Closed | 2022-12-16
22/16 | 2022-07-22 | 6 | Board to receive an update at a future meeting on progress with the real world evidence framework, including what is working well, any challenges and learning, and the progress with wider engagement on securing access to real-world data. | FG | 2023-05-01 | Update scheduled for May 2023. | Open | n/a
22/17 | 2022-07-22 | 7 | Board seminar to receive information on the plans for further income generation | BS | 2023-03-01 | Scheduled for the March board seminar. | Open | n/a
22/19 | 2022-09-22 | 4 | Board to receive an update on the work to develop a talent pipeline through the existing partnerships with universities on post-graduate courses. | HK | 2022-12-01 | Verbal update to be provided. | Open | n/a
22/20 | 2022-09-22 | 6 | Clarify the funding and commissioning arrangements for faecal microbiota transplant. | MC | 2022-10-01 | Referred to NHS England: Board will be advised as progresses. | Open | n/a
22/21 | 2022-09-22 | 7 | Further information to be provided to the Board on the balance between long-term and short-term sickness, and any differential in turnover according to banding and protected characteristics. | SR | 2022-10-01 | Information circulated to the Board by email on 6/10/22. | Closed | 2022-12-16
22/23 | 2022-09-22 | 7 | Review the reporting in the Integrated Performance Report (IPR) to provide a clearer overview of performance in the technology appraisal programme both in terms of income and operational delivery, and the extent the proportionate approach to appraisal priority is increasing capacity in the technology appraisal programme. | HK | TBC | Verbal update to be provided. | Open | n/a
22/24 | 2022-09-22 | 7 | Consider how the IPR can be evolved to provide more comprehensive insight into the implementation of NICE guidance. | JR | 2023-05-01 | Work on IPR metrics has commenced and Board will be updated by end of 2022/3. | Open | n/a
22/25 | 2022-09-22 | 7 | Review the approach to the ‘RAG’ ratings across the IPR to ensure clarity on when an indicator is shown as red or amber. | BS | 2022-12-01 | Summary slide amended in response to Board's feedback. | Closed | 2022-12-16
22/26 | 2022-09-22 | 9 | Board to receive a progress update on the EDI action plans, with staff networks invited to attend the discussion. | CPO | TBC | Update to scheduled once new CPO in post. | Open | n/a
22/27 | 2022-09-22 | 10 | Information on NICE’s health and safety (H&S) performance and implementation of the H&S policy to be reported to the Audit and Risk Committee on behalf of the Board. | CPO | 2023-05-01 | Annual report to be added to the ARC work plan. | Open | n/a