## Slide 1: Integrated performance report
July 2023

## Slide 2: Summary
Area
Confidence in achieving targets at year end
Comments
Our transformation
At the end of June 2023 there is high confidence in achieving the 8 objectives in the 2023/24 business plan, with all bar 2 of the 49 underpinning milestones on track.
High quality advice that is relevant, timely, usable and has a demonstrable impact
The guidance programmes are currently on track to deliver the volume of outputs in the business plan, with the guidelines programme ahead of plan.
At this early stage in the year, data is not yet available for some indicators but there are no significant concerns with the potential year-end out-turn.
While ensuring a financially sustainable organisation, with happy and well-supported staff, and effective communications and engagement
At the end of month 2, there was a £577k adverse variance to plan, primarily due to technology appraisals (TA) income being lower than plan. The current full year forecast is for the programme to recover £11m against an income target of £12.9m. A review is underway looking at capacity, activity and forecast, and will inform the forthcoming price review for 2024-25. The scope to utilise capacity in the TA team in other income generating areas of work is also being explored.
Turnover remains above target and a new exit interview provider will provide better insight and analysis of reasons for leaving. At this early stage in the year there are no significant concerns with the year-end forecast for the other people indicators or the communications and engagement indicators.

## Slide 3: Transformation
1 April 2023 to 30 June 2023

## Slide 4: Transformation Progress – July 2023 (Slide 1 of 6)
Focus on what matters most
1
Relevance
Objective 1
Increase the relevance of our guidance by developing a NICE-wide horizon scanning & topic selection function enabled by coordinated stakeholder engagement
Objective 2
Increase the real-world impact of our pre-evaluation support by simplifying and improving NICE’s early engagement with industry
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Draft Prioritisation Board ToR created
Task & finish group commissioned on prioritisation framework – criteria reflecting system need
Work completed on horizon scanning, system intelligence, & topic intelligence definitions
NICE engagement team management of change proposal presented to ET- final revisions in progress
Workshops held to identify and prioritise new engagement service approaches and opportunities
Completion of draft business model on future service design, commercial approach, and account management
Key risks and challenges
Ensuring effectiveness of changes to internal processes that enable effective integration of topic selection
Realising tangible changes in culture, behaviours, and skills that enable successful conversion of engagement activity into increases in income generation
Finding an impactful balance that maximises innovation in service offers to maximise income, while working within regulatory constraints
What we have learnt
Range of different approaches used across NICE for topic selection and horizon scanning – need for a shared vision and common language
Learning from external climate and competitor analysis - informing creative and tailored approaches to generate income
8 | Milestone | Delivered by | On track?
 | Adopted a new, coordinated approach to stakeholder engagement ​​ | Oct 2023​ | Yes​
 | Redesigned our support for developers and innovators to make the most of NICE’s relevant services, better tailored to the needs of all types of technology developers​​ | Oct 2023​ | Yes​
 | Established a new early engagement team bringing together all of NICE’s industry engagement services ​ | Oct 2023​ | Expected – 1 Nov​
 | Redesigned our business model to allow more scope for proactive outreach and to facilitate risk-based proportionate approaches to our advice for technologies ​ | Nov 2023​ | Yes​
 | Established new ways of working to systematically gather intelligence from the health and social care system, and from life sciences and industry ​​ | Jan 2024​ | Yes​
 | Created a cross-organisational prioritisation function ​​ | Jan 2024​ | Yes​
 | Established a new mechanism to scope and schedule our topics based on identified priorities ​​ | Jan 2024​ | Yes​
 | Tested our selected priorities with the health and care system ​ | Feb 2024​ | Yes​

## Slide 5: Transformation Progress – July 2023 (Slide 2 of 6)
Provide useful and useable advice – Part 1
2
Useable
Objective 3
Make our advice easier to access by improving our digital presence
Objective 4
Increase the useability of our guidance by incorporating technologies into guidelines, and evolve our supporting resource impact assessment
Objective 5
Improve the value of NHS purchasing in new ways by developing the programme to provide advice on classes of HealthTech products already in use
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Digital Presence
Selection and purchase of a new content management system (CMS) called Storyblok
We have continued to audit and cull old pages from the corporate website in order to make it easier to search and navigate.
The CCMS business case now has an updated cost-benefits analysis
User insight being distilled into what we know about key personas and typologies and what we plan to do address key needs.
DLG Process Simplifications
Diabetes and Women's & reproductive health suite/sub-suites have now been prioritised and validated
Process for recruiting faculties and recruiting committees from faculties refined​ and agreed for testing on mental health faculty.
TA Integration
Provisional decisions made about the approach to VAT and decision threshold
Some early discussions re: criteria for Integration vs. Incorporation held
Resource Impact Assessments
Agreed approach to new template with RIA.
Discussions taken place with clinicians in cancer services about gaps in current outputs.
Late-Stage Evaluations
Key principles to guide the methods work have been drafted and these will be signed off after feedback from DHSC during the next workshop. Work has begun on developing the methods for the project.
Key risks and challenges
Digital Presence
Delivery of product and channel strategy
Concerns raised at the OMC about CCMS benefits case hence procurement will be delayed
Collaborating with delivery teams to align business goals, user/stakeholder impacts, and team deliverables is crucial and needs ongoing focus.
DLG Process Simplification
Ensuring there is sufficient challenge around process improvement
TA Integration
Enabling delivery of rapid incorporation of newly published TAs will require changes to processes across Centres
Resource Impact Assessments
Inconsistency with information in economic assessments
Recognition in RIA team that templates too cumbersome for end users
What we have learnt
Digital Presence
Scale and scope of product & channel strategy needs clarification
Business case and product & channel strategy need closer alignment, and it is important to develop user personas and map delivery to them.
DLG Process Simplification
Full process optimisation will require digital tooling
TA Integration
Enabling delivery of rapid incorporation of newly published TAs will require changes to processes across Centres
Late-Stage Evaluations
The importance of alignment of key messages between key delivery partners (DHSC) as well as the use of common language.
Milestones are included on the next slide…

## Slide 6: Transformation Progress – July 2023 (Slides 3 of 6)
Provide useful and useable advice - Part 2
2
17 | Milestone | Delivered by | On track?
 | Agreed an approach to capturing and reporting evidence about the capacity and workforce implications of an intervention or recommendation | Jun 2023 | Yes
 | Commenced rolling quarterly improvements to guideline content presentation based on user research ​​ | Jul 2023 | Yes
 | Procured a new Content Management System to enable improvements to NICE’s corporate website | Aug 2023 | Yes
 | Aligned relevant methods and processes between guidelines and Technology Appraisals | Sept 2023 | Yes
 | Completed evidence review and initial stakeholder engagement to inform evaluative approach | Sept 2023 | Yes
 | Created a product and channel strategy to describe the future publishing model for NICE guidance that is more useful and useable | Oct 2023 | No
 | Commenced the continuous deployment and integration phase of our new CMS adoption | Oct 2023 | Yes
 | Procured suitable content management technology to realise our product strategy and deliver more value to our guidance users | Nov 2023 | No
 | Developed and adopted a Resource Impact Analysis methodology that reflects more granular evidence about capacity and workforce implications | Nov 2023 | Yes
 | Agreed and published interim methods and processes | Nov 2023 | Yes
 | Developed and tested a new presentation approach to illustrate the workforce and capacity implications of NICE advice | Nov 2023 | Yes
 | Developed and consulted on new methods and process to consider late-stage multi-tech evaluations | Dec 2023 | Yes
 | Developed an approach to accessing and utilising data for late-stage class-based evaluations | Dec 2023 | Yes
 | Launched two pilots of the new approach | Jan 2024 | Yes
 | Commenced 2 pilots of interim principles for integrating TAs in guidelines | Feb 2024 | Yes
 | Finalised and published the updated methods manual codifying the new approach | Mar 2024 | Yes
 | Developed partnerships for longer-term delivery of data access | Mar 2024 | Yes

## Slide 7: Transformation Progress – July 2023 (Slide 4 of 6)
Provide useful and useable advice - Part 3
Timely
Objective 6
Improve the timeliness of our guidance by implementing improvements to our methods and processes identified last year
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
A shortened approach to EVA has been developed and will be trialled in July and published in Aug.
Learning from the previous EVA pilot has been incorporated into the external assessment groups contract work package
Key risks and challenges
Further work with EAGs required to enable a smooth transition to new ways of working for Early Value Assessment
What we have learnt
10 | Milestone | Delivered by | On track?
 | Health tech: Launched the first topic under a new single approach to multi-technology evaluations across medtech, diagnostics, and digital, including incorporating quick wins identified in our Early Value Assessment pilots | Aug 2023 | Yes
 | Guidelines: Embedded pilot living mechanisms to monitor evidence & system intelligence for Key Priority Areas within diabetes & women’s health suites | Aug 2023 | Yes
 | Health tech: Defined the approach to including Resource Impact Statements alongside all health tech guidance | Oct 2023 | Yes
 | Medicines: Published a modular update to our methods and processes to embed improvements identified in our Proportionate Approach to Technology Appraisals in 2022/23 | Oct 2023 | Yes
 | Guidelines: Tested new proportionate approaches to guideline updates following identification of new evidence in Key Priority Areas in diabetes suite | Dec 2023 | Yes
 | Guidelines: Implemented a proportionate approach to consultation across all priority guideline suites | Jan 2024 | Yes
 | Medicines: Confirmed an approach to enable Rapid Entry to Managed Access | Jan 2024 | Yes
 | Medicines: Developed two reference models to test pathway appraisals in cancer medicines | Jan 2024 | Yes
 | Medicines: Commenced a pilot of a new approach to immuno-oncology appraisals/portfolio appraisals | Mar 2024 | Yes
 | Guidelines: Created a faculty of experts to support lifecycle of recommendations in 5 priority topic suites | Mar 2024 | Yes
2

## Slide 8: Transformation Progress – July 2023 (Slide 5 of 6)
Constantly learning from data and implementation
3
Learning from real
world data / Interlinked
Objective 7
Support implementation of our guidance by improving our measurement approach, and develop an automated uptake and monitoring system in a priority topic
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
​Planning​
Detailed project plan in place
Delivery group meetings fortnightly to monitor progress​
Topics prioritised for tracking uptake
7 groups of medicines and 5 children and young people topic areas agreed by the programme board. This is in addition to the 9 adult topics previously agreed. All prioritised based on alignment with system priorities (NHS planning guidance, Core20plus5, major conditions strategy)
Data identification and analysis​
All topic areas have aligned to quality standards.
Data sources mapped and available for 11 of 14 QS topics to date. Data extraction completed for 2 of these topics to date
Automation ​
Established a partnership with the Bennett institute to deliver a pilot project which will inform further work on automated measurement of NICE guidance
Reengaged an external expert group on computability to ensure input from thought leaders in the field
Key risks and challenges
Need to focus insight and outputs on the needs of our key audiences. We are developing hypotheses about the needs of users to test this through the work programme.
What we have learnt
Some ICBs have already made good progress with measurement, our unique selling point will be key.​
Measurement of the QS statement should not be limited to the included measures and can include both outcome and process measures.​
There are a number of interested parties with world-class expertise in computable guidance who are willing to engage with NICE's work.​
6 | Milestone | Delivered by | On track?
 | Assessed the extent of uptake of priority guidance using currently available data | Sep 2023 | Yes
 | Measured the uptake of NICE advice in a pilot priority topic using an automated reproducible pipeline | Nov 2023 | Yes
 | Develop an approach for automatic measurement of core recommendations in NICE guidance (HTA + guidelines) | Dec 2023 | Yes
 | Developed an approach for defining core computable recommendations for guidance | Mar 2024 | Yes
 | Implemented routine measurement of TAs and high impact/priority TAs quality standards as a surrogate for guideline uptake ​ | Mar 2024 | Yes
 | Established a system for routine feedback from uptake data to inform implementation support plans and topic selection | Mar 2024 | Yes

## Slide 9: Transformation Progress – July 2023 (Slide 6 of 6)
Build a brilliant organisation
4
Brilliant organisation
Objective 8
Build a brilliant organisation by implementing suggestions from crowdsourcing and staff survey including: develop a continuous improvement process and capabilities and adopt NICE-wide talent management approach
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Talent management: Ending period for completion of PDPs across organisation using new appraisal process. Evaluation designed to include in YW@N in July. Leadership competencies finalised. Development and engagement work for EDI road map is underway. Multiverse Data Academy cohort 1 launched.
Senior leaders' development: first in person session delivered, covering change with Kotter, brand and storytelling, and co-creation of development programme for senior leaders. Small group created to work up development programme for next 12-18 months.
NICE way: Proposals for development of 'NICE way' and the training of key cohorts discussed. Draft of tender and business case in progress.
Meeting spring clean month completed
Key risks and challenges
Still some work to bring along all those leading change across NICE with the unified approach of the 'NICE way'. We are reviewing collaboration and engagement. Business case and tender spec in progress.
What we have learnt
Early headline results of stress survey gave indication that change may be a source of stress for some staff. We will review and prioritise activities for the rest of the year in the next programme board. Full findings to be reported when available.
Positive engagement from at least 50% of senior leaders in community building and development planned for this year. Considering repeating session for others.
8 | Milestone | Delivered by | On track?
 | Defined and agreed the ‘NICE way’: a consistent cross organisational framework for continuous improvement at NICE | Sep 2023 | Yes
 | Completed our automation/AI strategy to improve our ways of working | Oct 2023 | Yes
 | Developed a 2-5 year Equality, Diversity and Inclusion roadmap | Nov 2023 | Yes
 | Developed and delivered training to develop improvement and change skills, at different levels within NICE | Nov 2023 | Yes
 | Redesigned our performance management process to streamline processes, embed management competencies and improve feedback | Dec 2023 | Yes
 | Launched a new intranet to support out transformation messaging and provide a networking and community building vehicle for staff | Dec 2023 | Yes
 | All directorates working with SharePoint instead of network drives on production of new information and docs | Dec 2023 | Yes
 | Developed a talent management approach including talent identification and succession planning | Jan 2024 | Yes

## Slide 10: Provide high quality advice, that is relevant, timely, usable, and has a demonstrable impact
1 April 2023 to 31 May 2023

## Slide 11: Provide high quality advice…
Chart: 110 technology appraisal and highly specialised technologies guidance
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22/23 | 6 | 5 | 12 | 9 | 10 | 6 | 10 | 10 | 7 | 6 | 12 | 8
2023/24 plan | YTD actual | Year-end forecast RAG status
110 | 17 | G
Expected to hit business plan target of 110 publications, however this does not reflect the level of activity and associated income levels required to achieve full cost recovery in 2023/24 (see finance update for further information).
Chart: 50 health technologies programme guidance
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan | 8 | 6 | 7 | 4 | 3 | 6 | 4 | 5 | 4 | 2 | 6 | 1
22/23 | 2 | 4 | 3 | 3 | 6 | 3 | 3 | 7 | 1 | 6 | 3 | 5
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
14 | 14 | 100% | G
Expected to reach target.

## Slide 12: Provide high quality advice…
Chart: 17 new guidelines or updates to topic suites
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 1 | 3 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1
Plan | 1 | 1 | 0 | 3 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0
22/23 | 2 | 2 | 4 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
3 | 7 | 233% | G
Expected to reach target.
Chart: 11 quality standard updates
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0 | 0
Plan | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 3 | 2 | 0 | 0
22/23 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 2 | 3
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
0 | 0 | 100% | G
Expected to reach target. No updates published in April or May.

## Slide 13: …that is relevant
Chart: Increase the proportion of early engagement services provided for diagnostics, devices and digital technologies by 25%
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0.294 | 0 | 0 | 0 | 0 | 0
Target for 23/24 out-turn | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36
22/23 out-turn | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
29% of engagements | 36% of engagements | 29.4% | A
Discussions are ongoing with health tech which are likely to lead to further projects, so target anticipated to be met at the year-end.
Chart: Prioritised strategic stakeholders have a named relationship lead
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 out-turn | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
0% | 80% | n/a% | G
The Executive Team agreed the prioritised strategic stakeholders in June 2023. Work is now underway to assign relationship leads and reporting on this will commence in July 2023.

## Slide 14: …that is timely
Chart: Days between GB marketing authorisation and final guidance publication: all topics
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 mean | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275
22/23 mean | 323 | 323 | 323 | 323 | 323 | 323 | 323 | 323 | 323 | 323 | 323 | 323
Overall 2022/23 mean | Target for 23/24 mean | YTD mean | Year-end forecast RAG status
323 days | 275 days (15% improvement) | 317 | G
Expected to hit target. Performance is calculated as YTD so reflects April and May.
Chart: Days between GB marketing authorisation and final guidance publication: ‘optimal’ topics
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 mean | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
22/23 mean | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55
Overall 2022/23 mean | Target for 23/24 mean | YTD mean | Year-end forecast RAG status
55 days | 90 days | n/a | G
No optimal topics published April and May.
Chart: Days between GB marketing authorisation and final guidance publication: ‘divergent’ topics
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 mean | 309 | 309 | 309 | 309 | 309 | 309 | 309 | 309 | 309 | 309 | 309 | 309
22/23 mean | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363
Overall 2022/23 mean | Target for 23/24 mean | YTD mean | Year-end forecast RAG status
363 days | 309 days (15% improvement) | 317 | G
Expected to hit target. Performance is calculated as YTD so reflects April and May.

## Slide 15: …that is timely
Chart: Time to produce health technology guidance is reduced by 17%
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 out-turn | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
22/23 out-turn | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
72 weeks | 60 weeks | 0 weeks | G
This target is expected to be reached with the development of a refreshed health tech guidance timeline. This timeline is currently in development and will be delivered by the end of the business year.
Chart: Conditional recommendations for early value assessments are produced within 6 months
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 out-turn | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
n/a | 80% | 0% | A
No EVAs have yet been published within the 6 month target this business year. The median time to produce conditional recommendations for the year is currently looking to be 6.8 months. But there is potential to identify time savings through the development of a refreshed health tech guidance timeline.
Chart: Evidence generation plans developed for all new EVA products, with conditional recommendations​
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 out-turn | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
n/a | 100% | 0% | A
Transitioning to new process of aligning plan publication with guidance, and still recruiting team to support plan production.

## Slide 16: …that is usable and has a demonstrable impact
Chart: Resource impact products published at the point of guidance publication to support implementation
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.9 | 0.9
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
22/23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
100% | 90% | 90% | G
Expected to hit target.
Chart: 10% increase in the number of sessions on nice.org.uk
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual YTD | -0.014 | 0.008
Target for 23/24 out-turn | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
22/23 out-turn | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
3.5% growth | 10% growth | 0.8% | A
NICE.org saw small growth in traffic year on year. This is attributable to both normal traffic fluctuations and a drop in NICE.org's performance on search engines. Planned work on the CMS and digital presence work should improve search engine performance. The number of sessions performed by users on the NICE site is a reflection of organisation wide factors.
Chart: System priority topic areas with agreed measures of uptake reported
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target for 23/24 out-turn | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
0% | 80% | 0% | G
System priority topic areas have been agreed. Work has begun to assess the data available within these areas.

## Slide 17: While ensuring a financially sustainable organisation, with happy and well-supported staff, and effective communications and engagement
1 April 2023 to 31 May 2023

## Slide 18: Financial position as at 31 May 2023
PAY £39k overspend Non-Pay £108k underspend Income £646k under recovery
Chart: 
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047
Actual | 4.5889 | 4.5854 | 4.5574 | 4.5592 | 4.5395 | 4.5676 | 4.5694 | 4.5876 | 4.5349 | 4.6104 | 4.5257 | 6.9697 | 4.8212 | 4.8152
Budget | 4.6661 | 4.607 | 4.6569 | 4.6419 | 4.668 | 4.6498 | 4.6402 | 4.6386 | 4.63 | 4.6372 | 4.6335 | 4.7471 | 4.8026 | 4.7944
Forecast | 1
Chart: 
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047
Actual | 1.6517 | 1.937 | 1.7721 | 1.6773 | 1.9624 | 1.835 | 2.4347 | 2.2222 | 2.2873 | 1.5757 | 1.817 | 2.9033 | 1.6636 | 1.7949
Budget | 1.7625 | 1.9806 | 1.9014 | 1.7703 | 1.9346 | 1.7954 | 2.1731 | 1.8592 | 1.9693 | 1.7573 | 1.7067 | 2.2397 | 1.7959 | 1.807
Forecast | 1
Chart: 
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047
Actual | 1.9695 | 1.9104 | 2.1398 | 2.1394 | 2.1907 | 1.8697 | 2.0319 | 1.8589 | 1.7005 | 1.6929 | 1.913 | 2.0311 | 1.895 | 1.7618
Target | 1.9128 | 1.8724 | 1.8341 | 1.856 | 1.856 | 1.835 | 1.9798 | 1.9594 | 1.9374 | 1.9594 | 1.9594 | 1.9527 | 2.1331 | 2.1698
Forecast | 1
Income: Technology Appraisal income is the key challenge YTD. A review is underway looking at capacity, activity and forecast, and this will inform the forthcoming price review for 2024-25. It was decided that a price increase during 2023-24 to reflect the additional pay award would not be applied to TA tariffs. NICE Scientific Advice has started the year with a small deficit at month 2 however the forecast is positive, and the deficit is forecast to move to a surplus in quarter 2.
Pay: is £39k over budget year to date. The majority of vacancies across teams were removed during budget setting for 2023-24 thus avoiding the underspend we saw across pay budgets in 2022-23. Pay is expected to remain on plan this financial year.
A pay contingency in 2023-24 of £800k has been used to part fund the settlement of a 5% pay award – directorate budgets assumed 3%. Funding for this settlement may be made available from the Department of Health and Social Care, however the amount we will receive is still to be agreed.
Non-Pay is £108k under budget year to date – a full year forecast will be completed after quarter 1 but this underspend is not expected to extrapolate in future months.
Reserves: As a result of TA performance, and uncertainty around funding for the pay award, discretionary in year investments are being reviewed, and a recruitment panel is being introduced to prioritise and review posts as vacancies arise.
Spend Category | Annual Budget £000 | Year to Date Budget £000 | Year to Date Actual £000 | Year to Date Variance £000
Pay | 59,264 | 9,597 | 9,636 | 39
Non-pay | 23,546 | 3,567 | 3,459 | (108)
Income | (25,989) | (4,303) | (3,657) | 646
Total | 56,822 | 8,861 | 9,438 | 577

## Slide 19: Technology Appraisals – Month 2
Year to date performance 2023-24
Month | Full cost recovery (£000) | Actual income (£000) | (Surplus)/Deficit (£000)
Apr-23 | 1,101 | 896 | 204
May-23 | 1,102 | 721 | 381
Total | 2,203 | 1,618 | 585
TA Income and Cost - YTD and Forecast
Chart: £000
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Direct costs | 724550.8317 | 727740.6552 | 727740.6552 | 727740.6552 | 727740.6552 | 727740.6552 | 727740.6552 | 727740.6552 | 727740.6552 | 727740.6552 | 727740.6552 | 727740.6552
Indirect costs | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884 | 202153.7884
Overheads | 173826.2175 | 172546.8342 | 172546.8342 | 172546.8342 | 172546.8342 | 172546.8342 | 172546.8342 | 172546.8342 | 172546.8342 | 172546.8342 | 172546.8342 | 172546.8342
Income | 896413.1 | 721190 | 873502.2976 | 854542.6466 | 758593.1855 | 815664.4187 | 1047955.3086 | 829140.8209 | 534354.6517 | 1203658.5201 | 1225006.0382 | 1239979.012
The year-to-date position is a £0.6m under recovery of income against expenditure. The programme has recovered 73% of its year-to-date costs. In 2022-23, 81% of costs were recovered.
The current full year forecast is to recover £11m against an income target of £12.9m. This is an early indication based on current work scheduling - topics could be added or removed through the year. Due to lower than planned activity a review is underway looking at any capacity in the TA team that could be used in other income generating areas of work.
The decision not to raise prices during 2023-24 to reflect the additional pay award, was made because it was felt a second price increase, in year, prior to a full pricing review in the Autumn was not the right course of action.
Forecast
Actual
Notes: Invitations to participate

## Slide 20: NICE Scientific Advice – Month 2
Year to date performance 2023-24
2023-24 YTD Actuals | £000
Expenditure | 542
Income | (459)
Variance - deficit | 83
Chart: NICE Scientific Advice income and expenditure between April 2022 - May 2023
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047
Expenditure | 216758.48 | 229180.23 | 224971.47 | 230112.07 | 237721.51 | 276470.1 | 240074.44 | 242997.43 | 265287.2 | 235717.49 | 234890 | 291594 | 262956 | 279457
Income | 245905.29 | 290491.53 | 355605.75 | 292387.49 | 317131.61 | 359775.8 | 252443.52 | 237524.7 | 257722.15 | 176435.08 | 254257 | 295361 | 243715 | 215429
NICE Scientific Advice (NSA) has generated a deficit of £83k at Month 2 in 2023-24.
The position at month 2 is lower than anticipated due to volatility in the work programme, which has resulted in a number of projects being delayed or cancelled at short notice. There is a strong pipeline for the scientific advice programme, and we expect to return to an overall surplus by month 4.
By October 2023 we are aiming to establish a new engagement team bringing together all of NICE’s industry engagement services – i.e. the Life Sciences, Scientific Advice and NICE International teams – into one team.

## Slide 21: Happy and well supported staff (Slide 1 of 3)
Chart: Sickness absence (proportion of WTE days reported as sickness)
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.0144 | 0.0176
Plan | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
Prior year | 0.0154 | 0.0131 | 0.0203 | 0.0204 | 0.02 | 0.0196 | 0.0191 | 0.0189 | 0.0188 | 0.0187 | 0.0188 | 0.0182
Average 2022/23 out-turn | Target for 23/24 out-turn | YTD % | Year-end forecast RAG status
1.89% | 2% | 1.6% | G
Current rates are below target.
Chart: Rate of staff turnover
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.11 | 0.1128
Target | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
22/23 | 0.1153 | 0.1136 | 0.1189 | 0.1247 | 0.1229 | 0.1272 | 0.1277 | 0.1248 | 0.1244 | 0.125 | 0.1217 | 0.1097
March 2023 | YTD | Year-end forecast RAG status
10.97% | 11.14% | R
A new exit interview provider will provide better insight and analysis of reasons for leaving.

## Slide 22: Happy and well supported staff (Slide 2 of 3)
Chart: Staff engagement scores remain good
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual
Target | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
Column1
Overall 2022/23 out-turn | Target for 23/24 | Latest score | Year-end forecast RAG status
n/a | >60% | n/a | G
Pulse survey closes on 7 July 2023.
Chart: 90% staff having completed an appraisal
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.0025 | 0.1089
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
22/23 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87
Overall 2022 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
87% | 90% | 11.14% | A
Percentage will continue increasing month on month as the appraisals are logged on ESR. Target to be met by the end of the appraisal period. Recording this data started in May 2023. Prior comparator is based on responses to 2022 staff survey.
Chart: 62% staff found their appraisal helpful
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual
Target | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62
22/23 out-turn | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57
Overall 2022 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
57% | 62% | n/a% | A
Pulse survey closes on 7 July 2023. Prior year comparator based on 2022 staff survey.

## Slide 23: Happy and well supported staff (Slide 3 of 3)
Chart: 20% increase in the proportion of ethnic minority staff at band 8a and above
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.1421 | 0.1448
Target for 23/24 out-turn | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667 | 0.1667
22/23 out-turn | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389 | 0.1389
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
13.89% | 16.67% | 14.35% | G
Target planned to be met by the end of the 23/24 year.
Chart: 20% increase in the proportion of ethnic minority staff at band 7 and above
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.1664 | 0.1714
Target for 23/24 out-turn | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913 | 0.1913
22/23 out-turn | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594 | 0.1594
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
15.94% | 19.13% | 16.99% | G
Target planned to be met by the end of the 23/24 year.

## Slide 24: Effective communications and engagement (Slide 1 of 3)
Chart: 85% of lay people who complete exit surveys rate their experience of working with NICE as ‘good’ or ‘excellent’ ​
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 1
Target for 23/24 out-turn | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85
22/23 out-turn | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
83% | 85% | 100% | G
No exit survey responses received for May.
Chart: 10% increase in subscriber acquisitions on 3 corporate newsletters
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
YTD Actual | 59997
Target for 23/24 out-turn | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220 | 63220
22/23 out-turn | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473 | 57473
Overall 2022/23 out-turn | Target for 23/24 out-turn | YTD | Year-end forecast RAG status
57,473 | 63,220 | 59,997 | G
Between April and May, NICE News for Health and Social Care increased from 39,733 to 40,139; Update for Primary Care increased from 14,513 to 14,640 and NICE News for Life Sciences increased from 5,154 to 5,218. Total subscribers at end of May was 59,997.

## Slide 25: Effective communications and engagement (Slide 2 of 3)
Chart: Complaints acknowledged and responded to in 20 working days
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
22/23 | 1 | 1 | 1 | 1 | 1
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
100% | 80% | n/a% | G
No complaints due for response in April and May.
Chart: Freedom of Information requests responded to within 20 working days
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 1 | 0.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
22/23 | 0.9 | 1 | 0.91 | 0.89 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.89
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
98% | 90% | 97% | A
Currently expected to meet target.
Chart: Parliamentary Questions (PQs) contribution provided within requested time frame
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.92 | 1
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
22/23 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0.96 | 1 | 1
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
99% | 90% | 97% | G
Currently expected to meet target.

## Slide 26: Effective communications and engagement (slide 3 of 3)
Chart: Proportion of media coverage of NICE that is positive
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.9 | 0.89
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
22/23 | 0.8 | 0.81 | 0.83 | 0.84 | 0.83 | 0.81 | 0.81 | 0.9 | 0.83 | 0.91 | 0.86 | 0.95
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
85% | 80% | 90% | G
Overall positive media coverage of NICE remains consistently high.
Chart: Proportion of NICE generated news coverage that includes at least one key message
| 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual | 0.455 | 0.437
Target | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
22/23 | 0 | 0 | 0.54 | 0.54 | 0.57 | 0.63 | 0 | 0.55 | 0.52 | 0.58 | 0.56 | 0.54
Overall 2022/23 out-turn | Target for 23/24 | YTD | Year-end forecast RAG status
56% | 60% | 45% | A
A limited number of press notices were issued in the first two months of the year so this number will rise as the prominence of our key messages in media coverage increases. The Press Office is working to further maximise key message coverage in all proactive comms.