## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
21/02 | 2021-01-27 | 21/009 | Board to receive further information on the measures that will be used to quantify the success of the Innovative Licensing and Access Pathway. | FG | 2021-10-01 | Update provided to the Board in July, with a view to discussing further at the board to board meeting with the MHRA in October. | Open | n/a
21/08 | 2021-03-24 | 21/023 | Board to receive an update on the work to develop business and marketing strategies for NICE International, along with a progress update on NICE International’s work more generally. | MB | 2021-07-01 | Progress update shared with the Board in July. | Closed | 2021-07-21
21/12 | 2021-03-24 | 21/027 | Board to receive further information on the work plan for the Office for Digital Health. | FG | 2021-06-01 | Workshop to explore NICE's role in digital health held with the NEDs. | Closed | 2021-07-21
21/19 | 2021-05-19 | 21/044 | Board to be updated on (a) the NICE Listens work on health inequalities, and (b) the activities on health inequalities more generally. | FG/JR | 2021-09-01 | High level overview of cross-institute health inequalities work provided at June board meeting, with a more detailed update scheduled for the September strategy session, which will include an update on NICE Listens. | Open | N/a
21/20 | 2021-05-19 | 21/046 | Board to be updated on the forecasting of expenditure and potential reallocation of resources in-year through the usual Board reporting. | JH | 2021-07-01 | Forecasting incorporated into the Integrated Performance Report initially presented to July Board | Closed | 2021-07-21
21/22 | 2021-05-19 | 21/047 | JG to confirm the extent of the increase in traffic to the NICE International page of the website, and if possible provide further analysis of what may have driven the increase. | JG | 2021-06-01 | A paid advertising campaign in April targeted at international, life sciences and guideline- user audiences drove traffic to the NI pages. The NI pages were also linked to the redesigned home page marking the 5-year strategy launch. This helped attract viewers. Analytics reports for June show 594 page views and 152 clicks on the 'call to action' tabs (including ‘contact us’, ‘request consultancy services’ and ‘book speaking engagements’). Top 3 countries visiting the pages: UK, Spain, United States. | Closed | 2021-07-21
21/23 | 2021-05-19 | 21/048 | Business plan to be issued following final review by DHSC. | GL | 2021-05-01 | Business plan issued following final approval by DHSC. | Closed | 2021-07-21
21/24 | 2021-05-19 | 21/050 | Audit and Risk Committee terms of reference to be amended as approved by the Board. | DC | 2021-05-01 | Updated ToR issued. | Closed | 2021-07-21