## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
22/06 | 2022-05-25 | 5 | Board to receive an update on hybrid working when qualitative and quantitative data is available on whether the working arrangements both provide flexibility for staff and support the delivery of the transformation programme. | HB | 2023-03-01 | Listening events have been held by ET with all staff. Staff are looking for information around hybrid contracts which we will provide. Staff will all require a contract addendum letter which we are required to do by law. Hybrid working in action seems to be working very well. | Closed | 2023-03-23
22/16 | 2022-07-22 | 6 | Board to receive an update at a future meeting on progress with the real world evidence framework, including what is working well, any challenges and learning, and the progress with wider engagement on securing access to real-world data. | FG | 2023-05-01 | Update scheduled for May 2023. | Open | n/a
22/17 | 2022-07-22 | 7 | Board seminar to receive information on the plans for further income generation | BS | 2023-05-01 | Scheduled for the May Board seminar. | Open | n/a
22/19 | 2022-09-22 | 4 | Board to receive an update on the work to develop a talent pipeline through the existing partnerships with universities on post-graduate courses. | HK/HB | 2023-07-01 | Following initial verbal update at December board, agreed that a further update should be provided as part of wider update on talent management when new CPO in post. This has been scheduled for July. | Open | n/a
22/24 | 2022-09-22 | 7 | Consider how the IPR can be evolved to provide more comprehensive insight into the implementation of NICE guidance. | CM | 2023-05-01 | Work on IPR metrics has commenced and Board will be updated by end of 2022/3. | Open | n/a
22/26 | 2022-09-22 | 9 | Board to receive a progress update on the EDI action plans, with staff networks invited to attend the discussion. | HB | 2023-05-01 | Update to be provided at the next Board meeting. | Open | n/a
22/27 | 2022-09-22 | 10 | Information on NICE’s health and safety (H&S) performance and implementation of the H&S policy to be reported to the Audit and Risk Committee on behalf of the Board. | HB | 2023-05-01 | Annual report added to the ARC work plan. | Open | n/a
22/28 | 2022-12-16 | 6 | Further information to be provided to the Board on the brand campaign aimed at commissioners from the Integrated Care Boards. | JG | 2023-01-01 | Brand campaign evaluation slides sent to Board members 20/2/2023. | Closed | 2023-03-22
22/29 | 2022-12-16 | 6 | CPO to review the current recruitment information on the NICE website and NHS jobs site to ensure this presents a welcoming and inclusive message to candidates from a diverse range of backgrounds. | HB | 2023-03-01 | Language etc will be reviewed in March as an immediate action. However there is a larger project for next year where we will be looking at any awards that we might apply for to demonstrate our commitment and action to diversity and inclusion here at NICE. | Closed | 2023-03-22
22/30 | 2022-12-16 | 7 | CPO to outline their perspective on what more NICE could do to reduce turnover, drawing on good practice elsewhere. | HB | 2023-07-01 | This is an area that is far reaching across all areas. There is much work that we are doing with people managers, looking at particular roles that are hard to attract and retain, and work on our culture. Update to be provided to the July Board meeting. | Open | n/a
22/31 | 2022-12-16 | 8 | Impact of using the existing flexibilities to adopt a broader societal perspective to be kept under review; with the Board receiving a progress update, including information on when a wider perspective has impacted recommendations, at a suitable future date. | FG | 2023-12-01 | Update scheduled for December 2023 Board meeting. | Open | n/a
22/32 | 2022-12-16 | 9 | Board to be kept informed of the impact of the health inequalities initiatives on the committees’ work and how NICE’s activities are impacting other health and care organisations. | CM | 2023-09-01 | Progress update scheduled for September public Board. | Open | n/a
22/33 | 2022-12-16 | 11 | Board to receive a further update on the phishing exercises. | AT | 2023-05-01 | Update to be provided to the Audit & Risk Committee and Board in May. | Open | n/a