## Slide 1: Integrated performance report
March 2023

## Slide 2: Summary
Area
Confidence in achieving targets at year end
Comments
Transformation
The business plan priorities - early value assessment of medtech, and proportionate approach to technology appraisal (TA) and transforming the way we work are all rated green/amber because although significant progress has been achieved this has fallen slightly short of original ambition and delays to the new IT helpdesk and digital committee recruitment. The digital living guideline priority is amber/red due to outcomes achieved being more modest than the original ambition, the objectives for DLG operating model have not been achieved.
Core advice and guidance
In addition to the work on NICE’s transformation, it is anticipated that the guidelines, technology appraisal and highly specialised technologies programmes will deliver the planned level of outputs set out in the business plan. The number of medical technologies guidance and medtech innovation briefings will be lower than set out in the business plan due to the number being routed to the programmes, while a small number of diagnostics and quality standards outputs originally planned for this year will now publish in 2023/24.
Timely access to new technologies
4 of the 6 targets for enabling timely access to new technologies through our TA and HST programmes are forecast green for year-end delivery. Accounting for the caveats that remove topics delayed by factors outside of NICE’s control, 1 TA topic exceeded the target time in appraisal due to capacity issues within NICE. Indicators are under review for 2023/24 to provide more comprehensive overview of performance.
Supporting implementation and adoption of our guidance
Both indicators on track – no issues to report. Consideration is currently being given to the best way of providing better insight into the adoption of NICE guidance.
Communications
3 of the 6 targets are forecast for green for year-end, including the proportion of media coverage that is positive and meeting the deadline for responding to parliamentary questions. Response times to enquiries is back on target, while the Freedom of Information target will not be met as it is 100% and 1 request was answered outside of timescale in each of April, June and July due to delays in identifying and processing the necessary information.
People
Sickness absence has reduced from August but remains higher than the start of the financial year, with stress the highest cause of absence. Staff turnover and vacancy rate continue to be above plan, with the Chief People Officer and HR team working closely with directorates to address this. Increasing the proportion of Black, Asian and minority ethnic staff in senior roles remains an area of focus and our aspiration is to see an annual increase of 20% in the representation of Black, Asian and minority ethic staff at bands 8 and above.
Finance
We are on track to deliver our statutory financial duties. The year-end forecast is a £0.7m underspend vs budget. This includes non-recurrent in-year spend of c.£1.6m to mitigate the forecast underspend and accelerate the delivery of key objectives. Income is forecast to increase £1.7m from last year, although TA income is forecast to be £0.4m below plan. Work is ongoing to identify efficiencies for 2023/24 through the business planning process.

## Slide 3: Transformation
1 April 2022 to 28 February 2023

## Slide 4: Transformation Progress February 2023 (Slide 1 of 4)
Focus on what matters most
1
Innovative methods
Proportionate
Approach to TA Evaluation
Expanding our capacity for
technology appraisal guidance
for medicines by 20% through developing a more
proportionate approach
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
The priority has reverted back to green – the latest reasonable estimates demonstrating an increase in capacity by 17% for 23/24, which is sufficient to meet the current demand in the pipeline. Changes to the pipeline are monitored monthly.
The Streamlined approach pilots continues with 5 topics now at final draft guidance or published guidance stage. There is a mixture of cancer and non-cancer topics and all have resulted in positive recommendations, giving patients faster access to the technologies by reducing the time spent in appraisal by approximately 25%.
Live pilot of pair appraisal approach on 2 drugs for chronic heart failure reached committee in January. Draft Guidance is out for consultation. It is currently under discussion as to which PATT approaches will be transitioned into business as usual and included as interim methods and processes from April 2023.
The HTA Lab explored options for rapid entry to managed access using a policy sandbox approach and has delivered a report capturing the learning. It is looking to pilot a streamlined approach to managed access, but a topic is yet to be identified. In the interim, it is testing the approach by re-running a topic that was previously recommended for managed access. HTA Lab is also leading a number of in-flight projects including Virtual Wards and disease modifying dementia treatments.
Key risks and challenges
There are an increasing number of commercial negotiations that the NHS and companies must undertake to support technology appraisal recommendations, which may limit how quickly we can progress. Therefore there is a risk that even if we speed up our own processes, we ultimately won't speed up patient access.
NICE does not manage which technologies progress through regulatory approval. As such we cannot guarantee sufficient topics will be suitable for new streamlined approaches. However, through the efforts of the PATT project we currently have more theoretical capacity for 23/24 compared to 22/23.
What we have learnt
Consideration as to how NICE acts as a price-shaper vs a price-taker will become more important for the Pathways pilots, as this will affect how commercial arrangements are best incorporated into the process. This will also be important for future PATT process developments.
Patient group meetings highlighted the need to consider the terminology used around streamlined approach, using the term 'proportionate' and not ‘remove’ will allay fears that input isn’t being inappropriately reduced.
Key performance indicator for 22/23 (from business plan) | Status
3 INDICATORS
HTA Lab approach trialled on at least 2 innovative, complex topics | 1 of 2
Proportionate approach piloted | Achieved
Proportionate (HTA Lab, conventional TA and simpler, faster approach) fully implementable from April 2023, providing a 20% increase in capacity to undertake TAs in 23/24 | In progress
Status key: Green – on track to achieve Amber – challenges to achieve with confidence in mitigation Red – Significant risk to achieve and limited confidence in mitigation

## Slide 5: Transformation Progress – February 2023 (Slide 2 of 4)
Create advice that’s useful and useable
2
Product innovation
Digital Living Guideline Recommendation
Improving the usefulness and
usability of our guidelines by publishing digital living guideline recommendations for breast cancer, with a new model of support for adoption of best practice
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Priority is reporting an amber/red low confidence rating, due to the outcomes achieved being more modest than the original ambition. The objectives for operating model have not been achieved. Full review of agreed milestones will be completed by end of March 2023.
Workstream 1 - Content and digital: Development of Component Content Management System (CCMS) business case underway. Development will continue into Q1 23/24.
Workstream 2 Pilot 1 - Breast Cancer: Evaluation of results from three projects. Artificial Intelligence (AI) surveillance tool outputs ratified with breast cancer experts.
Workstream 2 Pilot 2 - Women's Health and Diabetes: On-going recruitment to women's health suite faculty. Engagement with the Voluntary and Community Sector (VCS) forum on new proposed approaches to consultation recommendations.
Workstream 4 - Implementation: Implementation consultation with partners carried out and data sharing agreements in place for measurable data on Breast Cancer.
Key risks and challenges
The CCMS business case is being aligned with the CMS business care for website redesign.
There are some challenges to securing clinical input on the breast cancer pilot due to system pressures, the team are rescheduling around clinical availability.
What we have learnt
Testing of the Content Management System (CMS) has shown that it meets the usability and system requirements, this information will be useful as we go through soft market testing.
We have developed and tested a novel approach to consulting with teams to ensure living scope content is developed in line with user needs.
Key performance indicator for 22/23 (from business plan) | Status
3 INDICATORS
Interactive, digital living guideline recommendations on the breast cancer topic published on NICE website via a proof-of-concept platform | Achieved Published on internal platform
Deliver a bespoke implementation approach in partnership with national organisations, including a measurement framework | In progress
Organisational design to support the target operating model signed off for phased implementation | Red
Status key: Green – on track to achieve Amber – challenges to achieve with confidence in mitigation Red – Significant risk to achieve and limited confidence in mitigation

## Slide 6: Transformation Progress – February 2023 (Slide 3 of 4)
Create advice that’s useful and useable
2
Streamlined advice by topic
MedTech EVA
Actively drawing in medical devices, diagnostics and digital products that address national unmet needs and providing quicker assessments of early value to identify the most promising technologies conditional
on further evidence generation
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
The project has reverted to green with good progress towards 22/23 Key Performance Indicators (KPIs).
10 medtech topics have launched (KPI achieved).
2 publications achieved - children & young people mental health, and CariHeart (cardiac risk prediction). These are 2 of 5 medtech topics that were targeted to achieve publication by 31 March.
2 of the remaining 3 are on track for publication. The fifth (Kardiamobile) is also ready for publishing, but is delayed due to external DTAC requirements.
Completion of first draft evidence generation plan - children and young people.
Topic intelligence briefing for digital pulmonary rehabilitation finalised; further briefings in progress for mental health and social care technologies.
Resource plans within medtech and evidence generation complete.
Key risks and challenges
Stakeholder expectations – requirements such as DTAC and CE marking are impacting on progress of topics to publication.
Evidence generation plans - risk to delivery as stakeholder engagement is taking longer than anticipated – plans in place to recover the position during March.
What we have learnt
Need to clarify NICE’s role and respective partnership roles to maximise progress and impact – continuing to build on relationships to identify clear roles, increase efficiency and reduce duplication.
As part of the committee process, we will seek to gain greater clarity on evidence gaps and the rationale for their importance to better support creation of evidence generation plans.
Key performance indicator for 22/23 (from business plan) | Status
4 INDICATORS
10 medtech products (at least 6 of which will be digital) assessed | Achieved
5 products have published guidance | 2 of 5
Data collection workshops held and evidence generation plans developed for 60% of products that are conditionally recommended | In progress
Methods and resourcing in place to extend medtech early value assessment to all medtech in 23/24 | In progress
Status key: Green – on track to achieve Amber – challenges to achieve with confidence in mitigation Red – Significant risk to achieve and limited confidence in mitigation

## Slide 7: Transformation Progress – February 2023 (Slide 4 of 4)
To be an organisation as brilliant as the people in it
4
Behaviours, Processes and
Technology
Transforming the
way we work
Transformation of the way we work, including our technology, processes and behaviours
Confidence level in achieving objective
MEDIUM
HIGH
LOW
What’s been achieved
Reporting an amber status due to capacity challenges in deploying new helpdesk solution, which is replanned to launch late April 2023. Delay in development work by Civica relating to Trac committee recruitment. Escalated with Civica for a revised date to understand impact on rollout, which is now expected to be completed by late April 2023.
People and places are the first directorate to migrate to SharePoint, part of the Digital Workplace programme. This will be completed by end of March 2023.
98% of managers are enrolled on the management development course and feedback remains positive from virtual and face-to-face cohorts.
Implementation of formal hybrid working progressing and is to be implemented by mid-April 2023. Concerns raised by staff based at the London office in relation to HCAS payment are being addressed during March 2023.
Scope defined and plans produced in conjunction with ET leads for each golden bar, with the 3–5 year plan being agreed March 2023.
Key risks and challenges
Service ownership to support transformation – continue work to increase ownership and engagement with activity is underway, whilst laying foundations for ownership of new services in 23/24.
Staff feedback confirmed it is still unclear about when managers can direct staff to attend the office​ as part of hybrid working – further clarification being provided through March 2023.
What we have learnt
Revised change management approach for digital workplace, (whereby staff are being offered a greater level support), seen positive engagement and curiosity. Continued monitoring will inform approach and future learning.
Multiple communication channels and volume of messages has resulted in confusion. Standardising messages, including by audience has helped to achieve greater understanding and readiness for change.
Key performance indicator for 22/23 (from business plan) | Status
11
INDICATORS
Formal hybrid working introduced | Delayed until April 2023
Leadership/management development training rolled out | Achieved
Process improvement for consultation comments rolled out if pilot successful | Achieved
OneDrive rolled out as part of My Space service | Achieved
SharePoint established as the main platform for document management in at least 1 directorate | In progress
Priority objective projects are using Project Spaces as a service to support consistent standards and collaboration | Achieved
Fully integrated IT service desk is in place | Delayed until April 2023
AV/VC installed and working across the NICE estate | In progress
Digital committee recruitment tool rolled out if pilot successful | Delayed until April 2023
Target culture defined | Achieved
3-5 year roadmap for target culture and organisation-wide transformation approach produced | In progress

## Slide 8: Core advice and guidance
1 April 2022 to 31 January 2023

## Slide 9: Core advice and guidance (Slide 1 of 3)
Chart: 16 guidelines (new or updated)
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 2 | 2 | 4 | 2 | 0 | 1 | 1 | 1 | 1 | 1
Plan | 2 | 2 | 4 | 2 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1
Prior year | 3 | 0 | 2 | 2 | 4 | 0 | 2 | 4 | 3 | 3 | 0 | 7
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
14 | 15 | 107% | G
On track – no issues to report.
Chart: 98 technology appraisals and highly specialised technologies guidance
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 6 | 5 | 12 | 9 | 10 | 6 | 10 | 10 | 7 | 6
Prior year | 7 | 9 | 7 | 9 | 3 | 9 | 10 | 10 | 7 | 6 | 12 | 11
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
81 | 81 | 100% | G
The programme is forecast to publish 98 pieces of guidance across 22/23. Termination levels remain consistent with historical rates and this is not expected to adversely impact income recovery in the current year but is being closely monitored.
Chart: 33 interventional procedures guidance
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 2 | 4 | 3 | 2 | 5 | 3 | 2 | 5 | 0 | 4 | 0 | 0
Plan | 2 | 4 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 3
Prior year | 3 | 5 | 2 | 1 | 3 | 3 | 3 | 2 | 2 | 0 | 2 | 5
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
27 | 29 | 107% | G
On track – no issues to report.

## Slide 10: Core advice and guidance (Slide 2 of 3)
Chart: 7 diagnostics guidance
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Plan | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0
Year prior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 1
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
7 | 3 | 43% | A
One topic due to publish in October was delayed to allow for further work by the external assessment group and is now due to publish in March 2023. 3 other topics have been delayed due to a resolution request, correspondence from a stakeholder, and awaiting regulatory approval respectively; publication date for each is TBC but the programme anticipates publishing a total of 6 pieces of guidance in 2022/23 against 7 in the business plan.
Chart: 8 medical technologies guidance
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 0
Plan | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 1
Year prior | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 4
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
6 | 6 | 100% | A
The programme has 7 pieces of guidance planned to publish this financial year. It is unable to meet the target of 8 due to a decrease in appropriate topics in the topic pipeline, although the programme is also running several Early Value Assessment (EVA) pilots.
Chart: Up to 46 medtech innovation briefings
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 6 | 0 | 4 | 3 | 1 | 3 | 2 | 1 | 3 | 0 | 0
Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3
Year prior | 2 | 3 | 4 | 4 | 6 | 2 | 0 | 4 | 1 | 1 | 4 | 6
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
30 | 23 | 77% | A
The programme planned to publish at least 36 MIBs against the formal target of 46. The programme is slightly behind schedule in the final quarter due to the increase in team focus on Early Value Assessment (EVA) and a decrease in topics coming through horizon scanning. The programme is expected to complete the fourth quarter having published 30 MIBs, with a further 8 developed to publication stage; these 8 remain unpublished due to regulatory issues, company information and evidence or overlap with the emerging EVA programme.

## Slide 11: Core advice and guidance (Slide 3 of 3)
Chart: 11 quality standard updates
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 0
Plan | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 3 | 3
Prior year | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 3
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
5 | 4 | 80% | A
The QS programme has scheduled most of its 22/23 publications for the second half of the financial year. This scheduling reflects a pause in the programme during 21/22. 2 QS topics have been delayed, publication of these QS will fall into 23/24 giving a year-end total of 9 against the business plan target of 11.
Chart: 45 quality standard alignments
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 1 | 2 | 5 | 4 | 2 | 5 | 1 | 1 | 1 | 6 | 0 | 0
Plan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1
Prior year | 3 | 5 | 7 | 7 | 4 | 1 | 2 | 5 | 6 | 1 | 0 | 4
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
40 | 28 | 70% | A
The target is based on last year's activity. The programme is behind plan due to a few of the underpinning guidelines publishing later than expected. The year-end outturn is anticipated to be 38 against the business plan target of 45.
Chart: 1 indicator menu
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Plan | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prior year | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
YTD planned | YTD actual | YTD % | Year-end forecast RAG status
1 | 2 | 100% | G
Menu published in August 2022 in line with plan. Additional Indicator menu published in November 2022.

## Slide 12: Enabling timely access to new technologies through our technology appraisal and highly specialised technologies programmes
1 April 2022 to 31 January 2023

## Slide 13: Enabling timely access to new technologies through our technology appraisal and highly specialised technologies programmes (Slide 1 of 2)
Chart: Percentage of technology appraisals (TA) and highly specialised technologies evaluations (HST) for all new drugs with a new active substance referred to NICE issuing guidance within 90 days of the product being first licensed in the UK
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
Prior year | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1
YTD % | Year-end forecast RAG status
100% | G
7 new active substance topics which published November to January were excluded from the indicator as the caveats which remove topics affected by factors outside of NICE's control from the reporting applied.
Chart: Percentage of single technology appraisals and highly specialised technologies for all licence extensions issuing draft or final guidance within 6 months of the product being licensed in the UK
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0.33 | 1 | 1
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
YTD % | Year-end forecast RAG status
87% | G
2 topics in November which were terminations published outside of target due to internal NICE timescales. 8 topics which published November - January were excluded from the indicator as the caveats which remove topics affected by factors outside of NICE's control from the reporting applied. (new indicator for 22/23: prior year data not available)
Chart: Percentage of TA/HST evaluation topics at or below the relevant target time in appraisal set out in the guide to health technology evaluation
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 1 | 0.66 | 0.5 | 1 | 0.33 | 1 | 0 | 0.5 | 1
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
YTD % | Year-end forecast RAG status
71% | A
7 topics in November - January excluded as the caveats which remove topics affected by factors outside of NICE's control from the reporting applied. 12 terminations also removed. 1 topic in December missed the KPI due to NICE capacity issues. (new indicator for 22/23: prior year data not available).

## Slide 14: Enabling timely access to new technologies through our technology appraisal and highly specialised technologies programmes (Slide 2 of 2)
Chart: Percentage of TA/HST appeal panel decisions received within 3 weeks of the hearing
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Prior year | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
YTD % | Year-end forecast RAG status
100% | G
On track - no issues to report.
Chart: Percentage of TA/HST evaluation topics where post committee commercial activities have taken place which have draft guidance published within 63 days of committee recommendation
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 1 | 1 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 1
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
YTD % | Year-end forecast RAG status
63% | A
2 topics in November - January exceeded target: commercial briefings provided to NHSE within agreed timescale, but commercial discussions then took the topics beyond the usual timeline. (new indicator for 22/23 so prior year data not available).
Chart: Percentage of TA/HST evaluation topics where managed access activities have taken place which have draft guidance published within 63 days of committee recommendation
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 1 | 0.89 | 1 | 0.75 | 1 | 0.9 | 1 | 0.88 | 0.83 | 0.67
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
YTD % | Year-end forecast RAG status
89% | G
6 topics November to January exceeded target. Factors included complexity of the commercial negotiations, discussions around data collection, a tariff price impacting the appraisal needing to be finalised, and a topic not requiring a second committee meeting. (new indicator for 22/23 so prior year data not available).

## Slide 15: Supporting implementation and adoption of our guidance
1 April 2022 to 31 January 2023

## Slide 16: Supporting implementation and adoption of our guidance (Slide 1 of 1)
Chart: Resource impact products published to support all NICE guidelines (excluding COVID-19 rapid guidelines), positively recommended technology appraisals, medical technologies and diagnostics guidance at the point of guidance publication
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
Prior year | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
YTD % | Year-end forecast RAG status
100% | G
On track – no issues to report.
Chart: Percentage of planned availability of the NICE website, not including scheduled out of hours maintenance
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0.99 | 1 | 1 | 0.9999 | 1 | 1 | 1 | 0.999 | 1 | 100
Target | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98 | 0.98
Prior year | 0.9999 | 1 | 1 | 0.9987 | 0.9993 | 1 | 0.9996 | 0.9951 | 1 | 0.9995 | 1 | 1
YTD % | Year-end forecast RAG status
99% | G
On track – no issues to report.

## Slide 17: Communications
1 April 2022 to 31 January 2023

## Slide 18: Communications (Slide 1 of 2)
Chart: Complaints acknowledged and responded to in 20 working days
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 1 | 0 | 0 | 1 | 1 | 1
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Prior year | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1
YTD % | Year-end forecast RAG status
100% | G
On track – no issues to report.
Chart: Enquiries acknowledged and responded to in 18 working days
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0.9 | 0.9 | 0.68 | 0.68 | 0.68 | 0.93 | 0.94 | 0.95 | 0.95 | 0.95
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
Prior year | 0.89 | 0.9 | 0.94 | 0.97 | 0.95 | 0.89 | 0.89 | 0.93 | 0.91 | 0.93 | 0.91 | 0.93
YTD % | Year-end forecast RAG status
86% | A
During the summer, the team worked through a small backlog of cases caused by a combination of factors, including capacity issues. Recovery plans were put in place and since September each month's performance has been above target.
Chart: Freedom of Information requests responded to within 20 working days
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0.9 | 1 | 0.91 | 0.89 | 1 | 1 | 1 | 1 | 1 | 1
Target | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Prior year | 0.89 | 1 | 1 | 0.9 | 0.91 | 1 | 0.33 | 1 | 1 | 0.92 | 0.83 | 1
YTD % | Year-end forecast RAG status
98% | A
1 FOI answered late in each of the months April, June, and July due to delays in identifying and processing the necessary information.

## Slide 19: Communications (Slide 2 of 2)
Chart: Parliamentary Questions (PQs) contribution provided within requested time frame
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.96
Target | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
Prior year | 1 | 1 | 0.67 | 0.92 | 0 | 1 | 0.93 | 1 | 1 | 1 | 1 | 1
YTD % | Year-end forecast RAG status
98% | G
On track – no issues to report.
Chart: Proportion of media coverage of NICE that is positive
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0.8 | 0.81 | 0.83 | 0.84 | 0.83 | 0.81 | 0.81 | 0.9 | 0.83 | 0.91
Target | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Prior year | 0.84 | 0.83 | 0.84 | 0.75 | 0.57 | 0.77 | 0.88 | 0.83 | 0.86 | 0.87 | 0.83 | 0.81
YTD % | Year-end forecast RAG status
84% | G
The overall positive coverage for NICE remains consistently high and above target. The Press Office is continuing to look at innovative ways to maintain and improve established levels.
Chart: Proportion of NICE-generated news coverage includes at least one key message
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0 | 0 | 0.54 | 0.54 | 0.57 | 0.63 | 0 | 0.55 | 0.52 | 0.58
Target | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
YTD % | Year-end forecast RAG status
57% | A
Data collection began on 1 June 2022 so YTD average calculated from June. The new KPI is at an early stage but key messages are being reproduced in coverage. The Press Office are including key messages in all proactive releases.

## Slide 20: People
1 April 2022 to 31 January 2023

## Slide 21: People (Slide 1 of 2)
Chart: Rate of staff turnover
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0.1153 | 0.1136 | 0.1189 | 0.1247 | 0.1229 | 0.1272 | 0.1277 | 0.1248 | 0.1244 | 0.125
Plan | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09
Prior year | 0.086 | 0.0908 | 0.096 | 0.0984 | 0.1014 | 0.1064 | 0.1092 | 0.1087 | 0.1087 | 0.1252 | 0.1212 | 0.1233
January 2023 | Year-end forecast RAG status
12.5% | R
We are closely monitoring turnover for any trends and also reviewing exit data, and working with a new provider to refresh and relaunch the exit interview process to gain further insight into staff reasons for leaving. We are also working towards NICE being an employer of choice with various interventions from recruitment through to learning and development opportunities and organisational design. We are developing People plans with Directorates using workforce information data.
Chart: Vacancy rate
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0.0779 | 0.096 | 0.0795 | 0.0904 | 0.0652 | 0.07 | 0.071 | 0.075 | 0.0793 | 0.0829
Plan | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
Prior year | 0.119 | 0.116 | 0.115 | 0.115 | 0.111 | 0.094 | 0.095 | 0.091 | 0.092 | 0.078 | 0.0753 | 0.0779
January 2023 | Year-end forecast RAG status
8.29% | R
HR continue to work with Directorates to proactively manage their vacancies. Recruitment best practice training has been extended until November 2023. Hiring managers are required to attend before a recruitment campaign is launched.

## Slide 22: People (Slide 2 of 2)
Chart: Sickness absence (proportion of WTE days reported as sickness)
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0.0154 | 0.0131 | 0.0203 | 0.0204 | 0.02 | 0.0196 | 0.0191 | 0.0189 | 0.0188 | 0.0187
Plan | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
Prior year | 0.016 | 0.0151 | 0.0175 | 0.0173 | 0.0179 | 0.0181 | 0.0181 | 0.0185 | 0.0185 | 0.0264 | 0.0203 | 0.021
January 2023 | Year-end forecast RAG status
1.87% | G
Stress continues to be the highest cause of Sickness Absence at NICE. HR are proposing the introduction to the HSE Stress Management Standards which will provide methods in dealing with this at an organisational level.
Chart: Increase in the proportion of Black, Asian and minority ethnic staff in senior roles
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 0.13 | 0.13 | 0.14 | 0.14 | 0.14 | 0.14 | 0.13 | 0.14 | 0.13 | 0.13
January 2023 | Year-end forecast RAG status
13% | A
We are developing an action plan for year 2 of our organisational workforce objectives, which also includes areas of improvement identified in the WRES data. The areas of focus include: recruitment, developing an EDI training and development offer and the design and delivery of development offers for black, Asian and other minority ethnic staff who wish to progress. (new indicator for 22/23 so prior year data not available).

## Slide 23: Finance
1 April 2022 to 31 January 2023

## Slide 24: Financial position as at 31 January 2023
YTD PAY -£735,000 underspend YTD Non-Pay £452,000 overspend YTD Income -£501,000 surplus
Chart: 
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 4.5889 | 4.5854 | 4.5574 | 4.5592 | 4.5395 | 4.5676 | 4.5694 | 4.5876 | 4.5349 | 4.6104 | 4.5639 | 4.5938
Budget | 4.6661 | 4.607 | 4.6569 | 4.6419 | 4.668 | 4.6498 | 4.6402 | 4.6386 | 4.63 | 4.6372 | 4.6335 | 4.7471
Forecast | 1
£m
£m
£m
Chart: 
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 1.6517 | 1.937 | 1.7721 | 1.6773 | 1.9624 | 1.835 | 2.4347 | 2.2222 | 2.2873 | 1.5757 | 2.0855 | 2.3608
Budget | 1.7625 | 1.9806 | 1.9014 | 1.7703 | 1.9346 | 1.7954 | 2.1731 | 1.8592 | 1.9693 | 1.7573 | 1.7067 | 2.2397
Forecast | 1
Chart: 
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual | 1.9695 | 1.9104 | 2.1398 | 2.1394 | 2.1907 | 1.8697 | 2.0319 | 1.8589 | 1.7005 | 1.6929 | 2.0183 | 2.0999
Target | 1.9128 | 1.8724 | 1.8341 | 1.856 | 1.856 | 1.835 | 1.9798 | 1.9594 | 1.9374 | 1.9594 | 1.9594 | 1.9527
Forecast | 1
Pay is underspent due to the vacancy rate running at 8% vs a plan of 5%. Staff turnover is running at 12.5%.
Non-Pay year to date underspends accrued for travel and subsistence, course fees, and computer software/licenses have been offset with approved expenditure on non-recurrent investments in quarters 3 and 4. The spike in October relates to higher than planned BNF print costs. The Digital Workplace Programme is on plan YTD and is expecting to fully utilise available funding by year end. The drop in non-pay spend in January is related to prior year VAT rebates.
Income: NSA is delivering a £0.4m YTD over recovery against plan. TA income has a YTD £0.3m under recovery against plan. The fluctuation in income illustrated above are primarily driven by the projected work plan in the TA programme. The overall YTD surplus includes unplanned secondee income and a small surplus in SP&R.
Spend Category | Year to Date Budget £000 | Year to Date Actual £000 | Year to Date Variance £000
Pay | 46,436 | 45,700 | (735)
Non-pay | 18,904 | 19,356 | 452
Income | (19,002) | (19,504) | (501)
Total | 46,337 | 45,552 | (785)

## Slide 25: Forecast Outturn
Space for additional charts/images
Spend Category | Annual Budget £000 | Estimated Outturn Spend £000 | Estimated Outturn Variance £000
Pay | 55,816 | 54,870 | (946)
Non-pay | 22,850 | 22,205 | (645)
Investments (underspend) | - | 1,572 | 1,572
Income | (22,914) | (23,634) | (719)
Total | 55,752 | 55,013 | (739)
Based on the current run-rates extrapolated to the end of the financial-year, adjusted for expected changes in expenditure, income, and the successful delivery of planned investments, the forecast underspend for 2022-23 is £0.7m against a net budget of £55.8m.
Pay is set to continue to underspend, with an assumption that the vacancy rate of c8% will stay at a similar level for the remainder of the financial year. The 2022-23 pay award and recent Employer NI payment reduction are both reflected in the pay forecast.
Non-pay spend is forecast to increase in the latter part of the year, particularly in Digital (hardware purchases and audits/testing), and the variable element of the EAG contract. An element of non-pay expenditure, both year to date and in the forecast outturn, is related to contractor spend compensating for capacity gaps as a result of current vacancies.
Planned Investments – included in the forecast non-pay outturn are in year, approved, non-recurrent investments (c£1.6m) to mitigate the forecast underspend and accelerate the delivery of key objectives. There is a risk that some investments may slip due to capacity within teams, and procurement lead times, however the majority of projects have started and forecast spend has been reviewed with project leads and the commercial team.
TA income is on track to deliver £10.3m by year end (see next slide) against a plan of £10.7m. NSA are forecast to deliver a surplus of £0.4m by year end. Unplanned secondee income is £0.3m YTD.

## Slide 26: Technology Appraisals
Space for additional charts/images
YTD Performance | £'000
Income Target M1-10 | 8,800
Actual Income M1-10 | 8,478
Variance (under plan) | 322
Cumulative TA Income and Cost 2022-23
Chart: £000
| 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Actual income | 757.475 | 1433.7473 | 2481.6123 | 3520.0073 | 4642.1039 | 5387.7789 | 6233.6689 | 7020.0139 | 7716.0666 | 8477.7967 | 9433.7067 | 10286.5448
Income target (£10.7m) | 800 | 1600 | 2450 | 3300 | 4150 | 5000 | 5950 | 6900 | 7850 | 8800 | 9750 | 10700
Full cost recovery | 1044.2624 | 2038.9818 | 3074.872 | 4097.139 | 5139.64 | 6261.2061 | 7339.4725 | 8405.5684 | 9446.1685 | 10478.392 | 11513.4696 | 12553.0473
Year to date at month 10 we are reporting a £322k under recovery of income against plan. Using the TA planning database we are forecasting to be under the 22-23 income target of £10.7m with a forecast outturn of £10.3m. Year to date the programme has recovered 81% of its costs and is forecast to recover 82% by year end. In 2021-22, 75% of the cost recovery figure was met.
The reduced outturn is a result of topics in the work programme being removed, rescheduled, or paused following changes to regulatory timelines and evidence submission dates. Ongoing commercial discussions and pauses for further analyses of evidence also impact cost recovery.
The increase in TA fees from 1st April 2022 has begun to have an impact as milestones are completed for new appraisals, as the financial year has progressed.

## Slide 27: NICE Scientific Advice
 | Year to date Actuals £000 | Forecast Outturn £000
Expenditure | 2,399 | 2,911
Income | 2,785 | 3,312
Variance (Surplus) | -386 | -401
Chart: NICE Scientific Advice income and expenditure between April 2021 - March 2023
| 44287 | 44317 | 44348 | 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986
Expenditure | 193702.99 | 190492 | 209867 | 192246 | 181562 | 178408 | 192511 | 190380 | 219106 | 210186 | 206324 | 225927 | 216758.48 | 229180.23 | 224971.47 | 230112.07 | 237721.51 | 276470.1 | 240074.44 | 242997.43 | 265287.2 | 235717.49 | 255607.399 | 255607.399
Income | 168662.77 | 136378 | 172804 | 153078 | 110110 | 138095 | 190687 | 242952 | 259701 | 270598 | 231110 | 327960 | 245905.29 | 290491.53 | 355605.75 | 292387.49 | 317131.61 | 359775.8 | 252443.52 | 237524.7 | 257722.15 | 176435.08 | 240112.13 | 286849.73
Space for additional charts/images
NICE Scientific Advice (NSA) generated a surplus of £386k in the first 10 months of 2022/23, continuing the strong performance seen in the second half of the last financial year. The higher revenues can be attributed to continuing high levels of demand for early support services and increased technical capacity within the team.
Looking ahead, the team will be developing and testing new support services; optimising some of the existing services for digital and medtech products; and implementing a more balanced resourcing model to better manage capacity and demand. This development work will require resource from across the team and will need to be balanced against routine income-generating activities.
NICE International (NI) has a target to recover 75% of its costs through income generation (with the remaining amount covered by NSA). The team has generated income to cover 83% of its costs at month 10 (£185k). NI is forecast income is £261k against a plan of £295k.