## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
21/41 | 2021-11-17 | 9 | Further information to be provided to the Board on how the transferring staff from the NGA and NGC will support delivery of the new guidelines operating model, and the impact on the relationships with the two Royal Colleges. | PC | 2022-06-01 | Sustainable future operating models to accommodate new ways of working for guideline production are being explored as a workstream for the objective to deliver digital living guideline recommendations. An update will be provided in the context of this work in June. Round table for all NGC/NGA board members to be hosted by the CMO and Director of CfG to explore future working relationships in June. | Open | n/a
22/02 | 2022-03-17 | 6 | Integrated performance report to flag issues for the Board’s discussion, with the narrative noting, where appropriate, the longer-term position and direction of travel. | JH | 2022-05-01 | Noted for future reports. | Closed | 2022-05-25
22/03 | 2022-03-17 | 7 | Board to receive an update on the outcome of the consultation on the real world evidence framework and the next steps. | FG | 2022-10-01 | Consultation recently closed and currently being analysed. Further update on RWD use, including consultation outcomes and update on the next steps, to be provided to the Board in October. | Open | n/a
22/04 | 2022-03-17 | 8 | Board to be updated when the health inequalities oversight group has confirmed any changes to NICE’s approach in light of the NICE Listens recommendations. | JR | 2022-10-01 | NICE Listens recommendations complemented those from the external consultant who carried out an engagement exercise with strategic partners therefore recommendations have been incorporated into the health inequalities priorities for 2022/23. A progress update against the priorities will be reported to the board at the end of Q2. | Open | n/a