## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
22/16 | 2022-07-22 | 6 | Board to receive an update at a future meeting on progress with the real world evidence framework, including what is working well, any challenges and learning, and the progress with wider engagement on securing access to real-world data. | FG | 2023-05-01 | Update provided to May public Board meeting. | Closed | 2023-05-17
22/17 | 2022-07-22 | 7 | Board seminar to receive information on the plans for further income generation | BS | 2023-05-01 | Financial strategy discussed at May Board seminar. | Closed | 2023-05-17
22/19 | 2022-09-22 | 4 | Board to receive an update on the work to develop a talent pipeline through the existing partnerships with universities on post-graduate courses. | HK/HB | 2023-07-01 | Following initial verbal update at December Board, agreed that a further update should be provided as part of wider update on talent management when new CPO in post. This has been scheduled for July. | Open | n/a
22/24 | 2022-09-22 | 7 | Consider how the IPR can be evolved to provide more comprehensive insight into the implementation of NICE guidance. | CM | 2023-07-01 | New IPR indicators for implementation will be incorporated into 2023/24 reporting (first report July 2023). | Closed | 2023-05-17
22/26 | 2022-09-22 | 9 | Board to receive a progress update on the EDI action plans, with staff networks invited to attend the discussion. | HB | 2023-05-01 | EDI update to be provided at the May Board meeting. Staff networks to be invited to the September Board meeting when EDI is discussed in more detail with the annual equality report. | Closed | 2023-05-17
22/27 | 2022-09-22 | 10 | Information on NICE’s health and safety (H&S) performance and implementation of the H&S policy to be reported to the Audit and Risk Committee on behalf of the Board. | HB | 2023-05-01 | Annual report added to the ARC work plan. | Closed | 2023-05-17
22/30 | 2022-12-16 | 7 | CPO to outline their perspective on what more NICE could do to reduce turnover, drawing on good practice elsewhere. | HB | 2023-07-01 | This is an area that is far reaching across all areas. There is much work that we are doing with people managers, looking at particular roles that are hard to attract and retain, and work on our culture. Update to be provided to July Board meeting. | Open | n/a
22/31 | 2022-12-16 | 8 | Impact of using the existing flexibilities to adopt a broader societal perspective to be kept under review; with the Board receiving a progress update, including information on when a wider perspective has impacted recommendations, at a suitable future date. | FG | 2023-12-01 | Update scheduled for December 2023 Board meeting. | Open | n/a
22/32 | 2022-12-16 | 9 | Board to be kept informed of the impact of the health inequalities initiatives on the committees’ work and how NICE’s activities are impacting other health and care organisations. | CM | 2023-09-01 | Progress update scheduled for September public Board meeting. | Open | n/a
22/33 | 2022-12-16 | 11 | Board to receive a further update on the phishing exercises. | AT | 2023-05-01 | Update to be circulated to the Audit & Risk Committee in June. | Open | n/a
23/01 | 2023-03-22 | 6 | Life sciences marketing strategy to be circulated to the Board for information. | JG | 2023-03-01 | Strategy circulated to the Board | Closed | 2023-05-17
23/02 | 2023-03-22 | 6 | Board to receive further update on how much time has been taken out of the technology appraisal process for individual topics due to the streamlined approach and how much additional capacity has been generated. | HK | 2023-05-01 | Information circulated to the Board 9 May 2023. | Closed | 2023-05-17
23/03 | 2023-03-22 | 6 | Further information to be circulated to the Board on the non-recurrent expenditure to accelerate the business plan priorities. | BS | 2023-05-01 | Information circulated to the Board 9 May 2023. | Closed | 2023-05-17
23/04 | 2023-03-22 | 6 | Further update to be provided to the Board on the virtual wards initiative at a suitable point. | FG | 2023-07-01 | Update to be provided to the July public Board meeting. | Open | n/a
23/05 | 2023-03-22 | 6 | Further information on the lessons learnt from the 2022/23 business plan priorities to be presented to the Board alongside the 2023/24 business plan in May. | SR | 2023-05-01 | Information on lessons learnt from the 2022/23 business plan discussed at May Board seminar. | Closed | 2023-05-17
23/06 | 2023-03-22 | 7 | Report on the first year of implementation of the updated CHTE manual to include information on how the severity modifier has been applied, including for which conditions; information on the utilisation of the flexibilities around health inequalities; and the outcome of the work on committee consistency. | HK | 2023-12-01 | Update scheduled for December 2023 Board meeting. | Open | n/a