## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
21/41 | 2021-11-17 | 9 | Further information to be provided to the Board on how the transferring staff from the NGA and NGC will support delivery of the new guidelines operating model, and the impact on the relationships with the two Royal Colleges. | PC | 2022-09-01 | Sustainable future operating models to accommodate new ways of working for guideline production are being explored as a workstream for the objective to deliver digital living guideline recommendations. Progress update on the digital living guidelines priority presented to Board in June 2022, with further update provided to September board seminar. | Closed | 2022-09-22
22/04 | 2022-03-17 | 8 | Board to be updated when the health inequalities oversight group has confirmed any changes to NICE’s approach in light of the NICE Listens recommendations. | JR | 2022-10-01 | NICE Listens recommendations complemented those from the external consultant who carried out an engagement exercise with strategic partners therefore recommendations have been incorporated into the health inequalities priorities for 2022/23. A progress update against the priorities will be reported to the Board at the end of Q2. | Open | n/a
22/06 | 2022-05-25 | 5 | Board to receive an update on hybrid working when qualitative and quantitative data is available on whether the working arrangements both provide flexibility for staff and support the delivery of the transformation programme. | NG | TBC | Update to be provided in the new year. We will be recommencing hybrid working contract discussions with staff once the permanent CPO starts. | Open | n/a
22/09 | 2022-05-25 | 6 | Board to receive further information on whether the increased number of terminated guidance in 2021/22 is likely to be repeated in future years. | HK | TBC | Data currently being collected. | Open | n/a
22/10 | 2022-05-25 | 6 | Board to receive an update on the long-term funding mechanism for ILAP at a suitable point in the future. | HK | 2022-12-01 | Update to be provided towards the end of the calendar year. | Open | n/a
22/12 | 2022-05-25 | 7 | Board to discuss the lessons learnt from the work on dynamic living guidelines at a future seminar. | PC | 2022-09-01 | Update provided to the September board seminar. | Closed | 2022-09-22
22/15 | 2022-05-25 | 8 | Board to receive information on the results of phishing simulations undertaken at NICE. | AT | 2022-09-01 | An update on phishing simulation will be provided at the next Audit and Risk Committee in September. | Open | n/a
22/16 | 2022-07-22 | 6 | Board to receive an update at a future meeting on progress with the real world evidence framework, including what is working well, any challenges and learning, and the progress with wider engagement on securing access to real-world data. | FG | 2023-05-01 | Update scheduled for May 2023. | Open | n/a
22/17 | 2022-07-22 | 7 | Board seminar to receive information on the plans for further income generation | JH | 2022-12-01 | Scheduled for the December board seminar. | Open | n/a
22/18 | 2022-07-22 | 7 | Helen Knight to confirm when the first cohort of students are due to complete the NICE / LSE Masters course. | HK | 2022-09-01