- First draft Care Bundle (April 2015)

- Final CIWA-M (October 2018)

- Final guideline summary (Oct2018)

- Process Map (April 2015)

- Action Effect Diagram (April 2016)

- Alcohol related diagnoses (March 2017)

- Findings: doses given vs use of bundle

- Findings: duration of detox

- Summary of project recommendations

- Findings: run charts of diagnosis and length of stay (December 2018)

Alcohol withdrawal management on acute admission to hospital 
(and 24 hours later)
Supporting information
Adrian Brown
ade.brown@nhs.net

First Draft Care Bundle

Final version of CIWA-M

Final guideline summary

Process map (April 2015)

Action Effect Diagram (April 2016)

Alcohol related diagnoses (March 2017)

From poster presented to CLAHRC Learning Event

Findings: use of bundle

Full Data Set		352 	cases referred to Alcohol Care Team
Notes missing		-18 		(not found or on loan, no evidence in scans)

Exclusions		-127		(reasons for exclusion agreed before project)

ED ONLY		46

Not AAU		60

Not detox		19

Died	  		2

“Soft launch” cases	-109		(cases in data set, but before study care bundle finalised)

STUDY SAMPLE	 	98	/352

From these 98 cases

    - 53 	had Audit-C score clearly documented
(or sufficient info about frequency and amount of alcohol)

    - 45 	Care Bundle followed,

    - 37 	Care Bundle not followed, 16 CIWA not in notes

    - 11 	had no CIWA, 11 not started in first 24 hours

    - 9 	had no regular Chlordiazepoxide
7 	had no PRN Chlordiazepoxide
1 	had neither, but was prescribed Diazepam

    - 78 	were prescribed correct doses of Pabrinex
14 	had incorrect regimen or stopped too soon
6 	had no Pabrinex prescribed

    - 65 	received oral Thiamine afterwards
14 	received oral Thiamine with Pabrinex (>one day)
18 	received no oral Thiamine

Findings: duration of detox

    - Average length of stay

      - If care bundle followed		7 days

      - If care bundle NOT followed		9 days

    - Average duration of detox

      - If care bundle followed		5 days		51% complete by Day 6

      - If care bundle NOT followed		6 days		39% complete by Day 6

    - Average doses Chlordiazepoxide

      - If care bundle followed		134 mg to 106mg by Day 3

      - If care bundle NOT followed		116 mg to 115mg by Day 3

Final project recommendations:

- STANDARD PROCESS for individualised care

- USE OF AUDIT-C ?

- We need better detection of who to monitor with CIWA

- Will be part of national CQUIN for ALL admissions

- USE OF CIWA

- CIWA triggered starting dose can mean earlier completion of detox

- Can also allow for earlier recognition of untreated withdrawals

- Standard Chlordiazepoxide regimen plus CIWA triggered PRN

  - Avoids “missed doses”

  - Avoids confusion about what to prescribe

  - Standard Pabrinex & Thiamine regimen

  - Confusional states can be treated sooner

  - Should not be written up to end on Day 3, should be reviewed on Day 3

Findings: run charts of diagnosis alcohol dependence (December 2018 not fully complete, so ignore)

Y= number patients

Findings: run charts of monthly mean length of stay for these patients

Y= days